## Problem 8
[8 empty] | Total |  | Total
[8 empty] | Committed |  | Estimated
[7 empty] | Non- | and Non- | Estimated | Cost | Variance
|  |  |  | Total |  | Committed | Committed | Committed | Cost | at | Over /
|  | Original | Change | Estimate | Committed | Costs | Costs | Costs | To | Completion | (Under)
Code | Description | Estimate | Orders | (C + D) | Costs | Invoiced | Invoiced | (F + H) | Complete | (I + J) | (K - E)
2400 | Sanitary Sewer | 25000 | 3200 | 28200 | 0 | 0 | 27365 | 27365 | 0 | 27365 | -835
2450 | Water Line | 31000 | 0 | 31000 | 0 | 0 | 31300 | 31300 | 450 | 31750 | 750
2500 | Storm Drain | 17000 | 0 | 17000 | 0 | 0 | 7236 | 7236 | 9764 | 17000 | 0
2900 | Outside Lighting | 23600 | 0 | 23600 | 23600 | 11230 | 0 | 23600 | 0 | 23600 | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 | 0
|  | 96600 | 3200 | 99800 | 23600 | 11230 | 65901 | 89501 | 10214 | 99715 | -85

## Problem 9
[8 empty] | Total |  | Total
[8 empty] | Committed |  | Estimated
[7 empty] | Non- | and Non- | Estimated | Cost | Variance
|  |  |  | Total |  | Committed | Committed | Committed | Cost | at | Over /
|  | Original | Change | Estimate | Committed | Costs | Costs | Costs | To | Completion | (Under)
Code | Description | Estimate | Orders | (C + D) | Costs | Invoiced | Invoiced | (F + H) | Complete | (I + J) | (K - E)
2050 | Demolition & Grubbing | 30000 | 5000 | 35000 | 0 | 0 | 33562 | 33562 | 0 | 33562 | -1438
2100 | Grading & Excavation | 17500 | 2000 | 19500 | 0 | 0 | 17264 | 17264 | 2236 | 19500 | 0
2610 | Site Conc.-Labor | 19200 | 0 | 19200 | 19200 | 15200 | 0 | 19200 | 0 | 19200 | 0
2620 | Site Conc.-Concrete | 9900 | 0 | 9900 | 0 | 0 | 7425 | 7425 | 1950 | 9375 | -525
2700 | Landscaping | 37500 | 0 | 37500 | 37500 | 0 | 0 | 37500 | 0 | 37500 | 0
|  | 114100 | 7000 | 121100 | 56700 | 15200 | 58251 | 114951 | 4186 | 119137 | -1963

## Problem 10
[8 empty] | Total |  | Total
[8 empty] | Committed |  | Estimated
[7 empty] | Non- | and Non- | Estimated | Cost | Variance
|  |  |  | Total |  | Committed | Committed | Committed | Cost | at | Over /
|  | Original | Change | Estimate | Committed | Costs | Costs | Costs | To | Completion | (Under)
Code | Description | Estimate | Orders | (C + D) | Costs | Invoiced | Invoiced | (F + H) | Complete | (I + J) | (K - E)
1100 | Supervision | 36000 | 0 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0
1700 | Temporary Utilities | 6700 | 0 | 6700 | 0 | 0 | 0 | 0 | 6700 | 6700 | 0
1900 | Clean-up | 4600 | 0 | 4600 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0
3300 | Footing and Foundation—Labor | 3400 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 3400 | 0
3400 | Footing and Foundation—Concrete | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 3360 | 3360 | -140
3450 | Concrete Pump | 1700 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 1700 | 0
3500 | Slab/Floor—Labor | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 2100 | 0
3600 | Slab/Floor—Concrete | 6800 | 0 | 6800 | 0 | 0 | 0 | 0 | 6528 | 6528 | -272
3900 | Rebar | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 1100 | 0
4100 | Masonry | 44000 | 0 | 44000 | 42136 | 0 | 0 | 42136 | 0 | 42136 | -1864
5100 | Structural Steel | 11000 | 0 | 11000 | 10250 | 0 | 0 | 10250 | 0 | 10250 | -750
5300 | Joist and Deck | 15500 | 0 | 15500 | 15500 | 0 | 0 | 15500 | 0 | 15500 | 0
5900 | Erection | 8600 | 0 | 8600 | 8200 | 0 | 0 | 8200 | 0 | 8200 | -400
6110 | Rough Carpentry | 500 | 0 | 500 |  | 0 | 0 | 0 | 500 | 500 | 0
6120 | Lumber | 900 | 0 | 900 | 875 | 0 | 0 | 875 | 0 | 875 | -25
7200 | Insulation | 1700 | 0 | 1700 | 1802 | 0 | 0 | 1802 | 0 | 1802 | 102
7500 | Roofing | 9000 | 0 | 9000 | 8875 | 0 | 0 | 8875 | 0 | 8875 | -125
7700 | Roof Specialties | 1000 | 0 | 1000 | 945 | 0 | 0 | 945 | 0 | 945 | -55
8110 | Metal Doors and Frames | 2900 | 0 | 2900 | 2725 | 0 | 0 | 2725 | 0 | 2725 | -175
8400 | Store Fronts | 9500 | 0 | 9500 | 9100 | 0 | 0 | 9100 | 0 | 9100 | -400
8700 | Hardware | 1900 | 0 | 1900 | 1864 | 0 | 0 | 1864 | 0 | 1864 | -36
9100 | Drywall | 6700 | 0 | 6700 | 6898 | 0 | 0 | 6898 | 0 | 6898 | 198
9200 | Ceramic Tile | 2100 | 0 | 2100 | 1999 | 0 | 0 | 1999 | 0 | 1999 | -101
9300 | Acoustical Treatment | 7200 | 0 | 7200 | 6995 | 0 | 0 | 6995 | 0 | 6995 | -205
9400 | Carpet and Vinyl | 5500 | 0 | 5500 | 5354 | 0 | 0 | 5354 | 0 | 5354 | -146
9800 | Paint | 8200 | 0 | 8200 | 8000 | 0 | 0 | 8000 | 0 | 8000 | -200
10400 | Signage | 500 | 0 | 500 | 486 | 0 | 0 | 486 | 0 | 486 | -14
10800 | Toilet & Bath Accessories | 1000 | 0 | 1000 | 965 | 0 | 0 | 965 | 0 | 965 | -35
12300 | Cabinetry and Countertops | 10000 | 0 | 10000 | 9865 | 0 | 0 | 9865 | 0 | 9865 | -135
21100 | Fire Sprinklers | 6700 | 0 | 6700 | 7000 | 0 | 0 | 7000 | 0 | 7000 | 300
22100 | Plumbing | 24000 | 0 | 24000 | 22115 | 0 | 0 | 22115 | 0 | 22115 | -1885
23100 | HVAC | 23000 | 0 | 23000 | 23850 | 0 | 0 | 23850 | 0 | 23850 | 850
26100 | Electrical | 19000 | 0 | 19000 | 17825 | 0 | 0 | 17825 | 0 | 17825 | -1175
31100 | Grading and Excavation | 6300 | 0 | 6300 | 6150 | 0 | 0 | 6150 | 0 | 6150 | -150
32100 | Asphalt | 17000 | 0 | 17000 | 17569 | 0 | 0 | 17569 | 0 | 17569 | 569
32200 | Site Concrete—Labor | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0
32300 | Site Concrete—Concrete | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 960 | 960 | -40
32500 | Landscaping | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0
33100 | Sanitary Sewer | 1000 | 0 | 1000 | 1359 | 0 | 0 | 1359 | 0 | 1359 | 359
33200 | Water Line | 1000 | 0 | 1000 | 1125 | 0 | 0 | 1125 | 0 | 1125 | 125
| Profit and Overhead | 32000 | 0 | 32000 | 32000 | 0 | 0 | 32000 | 0 | 32000 | 0
|  | 346600 | 0 | 346600 | 271827 | 0 | 0 | 271827 | 68948 | 340775 | -5825

## Problem 11
[8 empty] | Total |  | Total
[8 empty] | Committed |  | Estimated
[7 empty] | Non- | and Non- | Estimated | Cost | Variance
|  |  |  | Total |  | Committed | Committed | Committed | Cost | at | Over /
|  | Original | Change | Estimate | Committed | Costs | Costs | Costs | To | Completion | (Under)
Code | Description | Estimate | Orders | (C + D) | Costs | Invoiced | Invoiced | (F + H) | Complete | (I + J) | (K - E)
1100 | Supervision | 36000 | 0 | 36000 | 0 | 0 | 7985 | 7985 | 28000 | 35985 | -15
1700 | Temporary Utilities | 6700 | 0 | 6700 | 0 | 0 | 1615 | 1615 | 5211 | 6826 | 126
1900 | Clean-up | 4600 | 0 | 4600 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0
3300 | Footing and Foundation—Labor | 3400 | 0 | 3400 | 0 | 0 | 3685 | 3685 | 0 | 3685 | 285
3400 | Footing and Foundation—Concrete | 3500 | 0 | 3500 | 0 | 0 | 3321 | 3321 | 0 | 3321 | -179
3450 | Concrete Pump | 1700 | 0 | 1700 | 0 | 0 | 1569 | 1569 | 0 | 1569 | -131
3500 | Slab/Floor—Labor | 2100 | 0 | 2100 | 0 | 0 | 1896 | 1896 | 0 | 1896 | -204
3600 | Slab/Floor—Concrete | 6800 | 0 | 6800 | 0 | 0 | 6955 | 6955 | 0 | 6955 | 155
3900 | Rebar | 1100 | 0 | 1100 | 0 | 0 | 999 | 999 | 0 | 999 | -101
4100 | Masonry | 44000 | 0 | 44000 | 42136 | 36000 | 0 | 42136 | 0 | 42136 | -1864
5100 | Structural Steel | 11000 | 0 | 11000 | 10250 | 0 | 0 | 10250 | 0 | 10250 | -750
5300 | Joist and Deck | 15500 | 0 | 15500 | 15500 | 0 | 0 | 15500 | 0 | 15500 | 0
5900 | Erection | 8600 | 0 | 8600 | 8200 | 0 | 0 | 8200 | 0 | 8200 | -400
6110 | Rough Carpentry | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 500 | 0
6120 | Lumber | 900 | 0 | 900 | 875 | 0 | 0 | 875 | 0 | 875 | -25
7200 | Insulation | 1700 | 0 | 1700 | 1802 | 0 | 0 | 1802 | 0 | 1802 | 102
7500 | Roofing | 9000 | 0 | 9000 | 8875 | 0 | 0 | 8875 | 0 | 8875 | -125
7700 | Roof Specialties | 1000 | 0 | 1000 | 945 | 0 | 0 | 945 | 0 | 945 | -55
8110 | Metal Doors and Frames | 2900 | 0 | 2900 | 2725 | 0 | 0 | 2725 | 0 | 2725 | -175
8400 | Store Fronts | 9500 | 0 | 9500 | 9100 | 0 | 0 | 9100 | 0 | 9100 | -400
8700 | Hardware | 1900 | 0 | 1900 | 1864 | 0 | 0 | 1864 | 0 | 1864 | -36
9100 | Drywall | 6700 | 0 | 6700 | 6898 | 0 | 0 | 6898 | 0 | 6898 | 198
9200 | Ceramic Tile | 2100 | 0 | 2100 | 1999 | 0 | 0 | 1999 | 0 | 1999 | -101
9300 | Acoustical Treatment | 7200 | 0 | 7200 | 6995 | 0 | 0 | 6995 | 0 | 6995 | -205
9400 | Carpet and Vinyl | 5500 | 0 | 5500 | 5354 | 0 | 0 | 5354 | 0 | 5354 | -146
9800 | Paint | 8200 | 0 | 8200 | 8000 | 0 | 0 | 8000 | 0 | 8000 | -200
10400 | Signage | 500 | 0 | 500 | 486 | 0 | 0 | 486 | 0 | 486 | -14
10800 | Toilet & Bath Accessories | 1000 | 0 | 1000 | 965 | 0 | 0 | 965 | 0 | 965 | -35
12300 | Cabinetry and Countertops | 10000 | 0 | 10000 | 9865 | 0 | 0 | 9865 | 0 | 9865 | -135
21100 | Fire Sprinklers | 6700 | 0 | 6700 | 7000 | 0 | 0 | 7000 | 0 | 7000 | 300
22100 | Plumbing | 24000 | 0 | 24000 | 22115 | 0 | 0 | 22115 | 0 | 22115 | -1885
23100 | HVAC | 23000 | 0 | 23000 | 23850 | 0 | 0 | 23850 | 0 | 23850 | 850
26100 | Electrical | 19000 | 0 | 19000 | 17825 | 0 | 0 | 17825 | 0 | 17825 | -1175
31100 | Grading and Excavation | 6300 | 0 | 6300 | 6150 | 3150 | 0 | 6150 | 0 | 6150 | -150
32100 | Asphalt | 17000 | 0 | 17000 | 17569 | 0 | 0 | 17569 | 0 | 17569 | 569
32200 | Site Concrete—Labor | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0
32300 | Site Concrete—Concrete | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 960 | 960 | -40
32500 | Landscaping | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0
33100 | Sanitary Sewer | 1000 | 0 | 1000 | 1359 | 0 | 0 | 1359 | 0 | 1359 | 359
33200 | Water Line | 1000 | 0 | 1000 | 1125 | 0 | 0 | 1125 | 0 | 1125 | 125
| Profit and Overhead | 32000 | 0 | 32000 | 32000 | 0 | 0 | 32000 | 0 | 32000 | 0
|  | 346600 | 0 | 346600 | 271827 | 39150 | 28025 | 299852 | 41271 | 341123 | -5477