## ProjCrashing
CHAPTER 3: Example 12
Project Management |  |  | Crashing
Results
Data |  |  |  | Normal time | 15 | [5 empty] | Minimum crash cost to meet project goal | 0
Project goal | 13 |  |  | Minimum time | 7 | [5 empty] | Project time
[5 empty] | Immediate Predecessors (1 per column) | [5 empty] | Intermediate Computations
Activity | Normal Time | Normal Cost | Crash Time | Crash Cost | Pred 1 | Pred 2 | Pred 3 | Pred 4 |  | Crash days | Crash cost/day | Crash limit
A | 2 | 22000 | 1 | 22750 | [5 empty] | 0 | 750 | 1
B | 3 | 30000 | 1 | 34000 | [5 empty] | 0 | 2000 | 2
C | 2 | 26000 | 1 | 27000 | A |  |  |  |  | 0 | 1000 | 1
D | 4 | 48000 | 3 | 49000 | A | B |  |  |  | 0 | 1000 | 1
E | 4 | 56000 | 2 | 58000 | C |  |  |  |  | 0 | 1000 | 2
F | 3 | 30000 | 2 | 30500 | C |  |  |  |  | 0 | 500 | 1
G | 5 | 80000 | 2 | 84500 | D | E |  |  |  | 0 | 1500 | 3
H | 2 | 16000 | 1 | 19000 | F | G |  |  |  | 0 | 3000 | 1
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Precedence computations | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 if col precedes row | A | B | C | D | E | F | G | H | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx
A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Normal time | 2 | 3 | 2 | 4 | 4 | 3 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TimeFinish (variable) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
crash days (variable) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
limit | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crash days | Finish Times for Tasks must be greater than finish for all predecessors | Finish A + T(row)-crash row | Finish B + T(row)-crash row | Finish C + T(row)-crash row | Finish D + T(row)-crash row | Finish E + T(row)-crash row | Finish F + T(row)-crash row | Finish G + T(row)-crash row | Finish H + T(row)-crash row | Finish I + T(row)-crash row | Finish J + T(row)-crash row | Finish K + T(row)-crash row | Finish C + T(row)-crash row
0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data
| Time | Precedence 1 | Precedence 2 | Precedence 3 | Precedence 4
A | 2 | 0 | 0 | 0 | 0
B | 3 | 0 | 0 | 0 | 0
C | 2 | A | 0 | 0 | 0
D | 4 | A | B | 0 | 0
E | 4 | C | 0 | 0 | 0
F | 3 | C | 0 | 0 | 0
G | 5 | D | E | 0 | 0
H | 2 | F | G | 0 | 0
Results
Task | Early Start | Early Finish | Late Start | Late Finish | Slack
A | 0 | 2 | 0 | 2 | 0 |  | 0 | 0 | 0 | 0 | 0
B | 0 | 3 | 1 | 4 | 1 |  | 0 | 0 | 0 | 0 | 0
C | 2 | 4 | 2 | 4 | 0 |  | 0 | 0 | 0 | 0 | 0
D | 3 | 7 | 4 | 8 | 1 |  | 0 | 0 | 0 | 0 | 0
E | 4 | 8 | 4 | 8 | 0 |  | 0 | 0 | 0 | 0 | 0
F | 4 | 7 | 10 | 13 | 6 |  | 0 | 0 | 0 | 0 | 0
G | 8 | 13 | 8 | 13 | 0 |  | 0 | 0 | 0 | 0 | 0
H | 13 | 15 | 13 | 15 | 0 |  | 0 | 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| G: 0; H: 0 | 0 | 0 | 0
| A: Project; B: 15; G: 0; H: 0 | 0 | 0 | 0
Early start computations | G: 0; H: 0
A | B: 0; C: 0; D: 0; E: 0
B | B: 0; C: 0; D: 0; E: 0
C | B: 2; C: 0; D: 0; E: 0
D | B: 2; C: 3; D: 0; E: 0
E | B: 4; C: 0; D: 0; E: 0
F | B: 4; C: 0; D: 0; E: 0
G | B: 7; C: 8; D: 0; E: 0
H | B: 7; C: 13; D: 0; E: 0
Late finish computations
| A | B | C | D | E | F | G | H
A | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0
B | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 1 | 1 | 1 | 1 | 1
C | 2 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 2 | 2 | 2 | 2 | 2
D | 4 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 4 | 4 | 4 | 4 | 4
E | 15 | 15 | 4 | 15 | 15 | 15 | 15 | 15 | 4 | 4 | 4 | 4 | 4
F | 15 | 15 | 10 | 15 | 15 | 15 | 15 | 15 | 10 | 10 | 10 | 10 | 10
G | 15 | 15 | 15 | 8 | 8 | 15 | 15 | 15 | 8 | 8 | 8 | 8 | 8
H | 15 | 15 | 15 | 15 | 15 | 13 | 13 | 15 | 13 | 13 | 13 | 13 | 13
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 2 | 4 | 4 | 8 | 8 | 13 | 13 | 15 | 0 | 0 | 0 | 0 | 0
Project Management
Data
| Time | Precedence 1 | Precedence 2 | Precedence 3 | Precedence 4
A | 1 | 0 | 0 | 0 | 0
B | 1 | 0 | 0 | 0 | 0
C | 1 | A | 0 | 0 | 0
D | 3 | A | B | 0 | 0
E | 2 | C | 0 | 0 | 0
F | 2 | C | 0 | 0 | 0
G | 2 | D | E | 0 | 0
H | 1 | F | G | 0 | 0
Results | D: 7
Task | Early Start | Early Finish | Late Start | Late Finish | Slack
A | 0 | 1 | 0 | 1 | 0
B | 0 | 1 | 0 | 1 | 0
C | 1 | 2 | 1 | 2 | 0
D | 1 | 4 | 1 | 4 | 0 |  | 3 | 1
E | 2 | 4 | 2 | 4 | 0
F | 2 | 4 | 4 | 6 | 2
G | 4 | 6 | 4 | 6 | 0
H | 6 | 7 | 6 | 7 | 0
| Project | 7
Early start computations
A | B: 0; C: 0; D: 0; E: 0
B | B: 0; C: 0; D: 0; E: 0
C | B: 1; C: 0; D: 0; E: 0
D | B: 1; C: 1; D: 0; E: 0
E | B: 2; C: 0; D: 0; E: 0
F | B: 2; C: 0; D: 0; E: 0
G | B: 4; C: 4; D: 0; E: 0
H | B: 4; C: 6; D: 0; E: 0
Late finish computations
| A | B | C | D | E | F | G | H
A | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 1 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
D | 1 | 1 | 7 | 7 | 7 | 7 | 7 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
E | 7 | 7 | 2 | 7 | 7 | 7 | 7 | 7 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
F | 7 | 7 | 4 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G | 7 | 7 | 7 | 4 | 4 | 7 | 7 | 7 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
H | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 1 | 1 | 2 | 4 | 4 | 6 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enter the data in the shaded area. Then go to the DATA Tab on the ribbon, click on Solver in the Data Analysis Group and then click SOLVE.
If SOLVER is not on the Data Tab then please see the Help file (Solver) for instructions.