## Sheet1
Video Game Delivery Project Cost Estimate
| # Units/Hrs. | Cost/Unit/Hr. | Total | Subtotals | % of Total | Internal Labor | Outsourced Costs
WBS Items
Project Management (internal)* |  |  |  | 109000 | 21.8%
Project manager | 790 | 100 | 79000 |  |  | 79000
Team members | 500 | 60 | 30000 |  |  | 30000
Requirements Definition |  |  | 0 | 36000 | 7.2%
Internal team | 400 | 60 | 24000 |  |  | 24000
Outsourced labor | 100 | 120 | 12000 |  |  |  | 12000
Off-the-Shelf System Installation |  |  | 0 | 172000 | 34.4%
Internal team | 300 | 60 | 18000 |  |  | 18000
Outsourced labor | 200 | 120 | 24000 |  |  |  | 24000
Hardware |  |  | 50000 |  |  |  | 50000
Purchased software |  |  | 80000 |  |  |  | 80000
System Customization |  |  | 0 | 93000 | 18.6%
Internal team | 750 | 60 | 45000 |  |  | 45000
Outsourced labor | 400 | 120 | 48000 |  |  |  | 48000
Testing |  |  | 0 | 48000 | 9.6%
Internal team | 400 | 60 | 24000 |  |  | 24000
Outsourced labor | 200 | 120 | 24000 |  |  |  | 24000
Training, Roll Out, and Support |  |  | 0 | 42000 | 8.4%
Internal team | 500 | 60 | 30000 |  |  | 30000
Outsourced labor | 100 | 120 | 12000 |  |  |  | 12000
Total project cost estimate |  |  |  | 500000 |  | 250000 | 250000
Assumptions
* The PM also assisted in other areas, but all of his costs are included in the project management category.
Estimated number of hours and cost/hour are shown above.
The percentage of each WBS item to the total seem reasonable.
Costs are split 50/50 between internal and external sources.
The hardware and purchased software costs ar based on vendor quotes.

## Sheet2
* Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898