Chapter

02-108

2 	Project Management

A. Project Management Across the Organization

TEACHING TIP

Introduce with XBOX 360.  Four years after the introduction of Xbox, Microsoft needed to design, develop, and produce a new product quickly.  Developing such as product is a project of massive proportions.  The project consisted of four phases: design, analysis, development, and launch.

- A project is an interrelated set of activities that has definite starting and ending points and that result in a unique product or service.

  - Common everyday life

    - Planning weddings

    - Remodeling bathrooms

    - Writing term papers

    - Organizing surprise parties

  - Business

    - Conducting audits

    - Planning mergers

    - Creating advertising campaigns

    - Reengineering processes

    - Developing new products or services

    - Establishing a strategic alliances

  - Three main goals of any project

    - Complete the project on time or early

    - Do not exceed the budget

    - Meet the specifications to the satisfaction of the customers

- Project management is a systemized, phased approach to defining, organizing, planning, monitoring, and controlling projects, as a means to overcome the challenge.

- Projects can be used to implement changes to operations strategy

- Projects can also be used to implement changes to processes and value chains.

- Projects may be under the overall purview of a single department, other departments likely should be involved in the project.

Cross-functional interaction example: Consider an information systems project to develop a corporate customer base.

02-109

  - Corporate banking services could be designed not only to better serve the corporate customers, but also to provide a basis for evaluating the prices that the bank charges.

  - Marketing is interested in knowing the services a customer is receiving so that it can package and sell other services that the customer may not be aware of.

  - Finance is interested in how profitable a customer is to the bank and whether the provided services are appropriately priced.

B. Defining and Organizing Projects

Successful projects begin with a clear definition of scope, objectives, and activities.  A successful project begins with clear understanding of its organization and how people are going to work together to complete the project.  In this section, the three important activities are discussed.

- Define the scope and objectives of a project

  - Statement of scope (also known as the project objective statement)

    - Statement of project objectives

    - Captures the essence of the desired project outcomes in the form of major deliverables

    - These deliverables become the focus of management attention during the life of the project

    - Important to avoid or manage scope creep, the ongoing changes to project scope that may, in sufficient quantity cause time delay and failure.

  - Time frame: as specific as possible.

  - A specific statement of allocated resources in terms of dollars and/or full-time equivalents of personnel time.

- Select the project manager and team

  - Project manager—has the responsibility to integrate the efforts of people from various functional areas to achieve specified project goals.

    - Roles of the project manager

      - Facilitator

      - Communicator

      - Decision maker

    - Characteristics

      - Technical competence

      - Sensitivity

      - Dedication

Project team—a group of people that often represent different functional areas or organizations.

02-110

- Organizational structure

  - Functional

  - Pure Project

  - Matrix:  compromise between functional and pure project

C. Planning Projects

After the project is defined and the project organized, the team must formulate a plan that identifies the specific activities to be accomplished and a schedule for their completion.  Planning projects involve five steps.

- Defining the work breakdown structure (WBS)

  - A statement of all work that has to be completed.

  - Identify all work activities.

  - Generate a hierarchy to the work breakdown: major work components are broken down to smaller activities.

  - Activities are the smallest unit of work effort that consumes both time and resources that a project manager can schedule and control.

  - Each activity in the WBS must have an “owner” who is responsible for doing the work.

- Diagramming the network.

  - Network planning methods can help managers monitor and control projects.

  - These methods treat a project as a set of interrelated activities that can be visually displayed in a network diagram consisting of nodes and arcs.

  - Two planning methods were developed in the 1950s.

    - Program evaluation and review technique (PERT)

    - Critical path method (CPM)

    - Although earlier versions differed, today the differences are minor. Hence in this book for the purpose of discussion they are referred to collectively as PERT/CPM.

    - Benefits to project managers

  - Establishing precedence relationships

  - Estimating activity times

    - Statistical methods (see Supplement H, “Measuring Output Rates,” in myomlab)

    - Learning curve models (see Supplement I, “Learning Curve Analysis,” in myomlab)

    - Using managerial opinions (see Chapter 13, “Forecasting”)

  - Using the Activity-on-Node (AON) approach

    - Nodes are activities and arcs show precedence relationships

Activity-oriented

02-111

    - Use Example 2.1: Diagramming the St. John’s Hospital Project

    - Use Application 2.1 (note: this is problem 2)

The following information is known about a project

| Activity | Activity Time (days) | Immediate Predecessor(s) |
| --- | --- | --- |
| A | 7 | -- |
| B | 2 | A |
| C | 4 | A |
| D | 4 | B, C |
| E | 4 | D |
| F | 3 | E |
| G | 5 | E |

Draw the network diagram for this project

B

2

F

3

A

7

D

4

E

4

Start

Finish

C

4

G

5

- Developing the schedule

  - The critical path is the sequence of activities between a project’s start and finish that takes the longest time to complete

  - Project schedule is specified by the start and finish times for each activity.

    - Earliest start time (ES)

    - Earliest finish time (EF)

EF = ES + t

    - Latest start time (LS)

LS = LF – t

    - Latest finish time (LF)

LF =	Earliest of the [LS times for all immediately following activities]

  - Project schedule

    - Gantt chart

    - Microsoft Project

    - Use Example 2.2: Calculating Start and Finish Times for the Activities

    - Active Model 2.2 in myomlab provides additional insight on Gantt charts and their uses for the St. John’s Hospital project (example 2.1).

Activity slack is calculated from four times for each activity

02-112

    - Activity slack: maximum time an activity can be delayed without delaying the entire project

    - Activity slack can be calculated in one of two ways

S = LS – ES or S = LF– EF.

    - Activities on the critical path have with zero slack

  - Use Application 2.2 (note: this is problem 2)

Calculate the four times for each activity in order to determine the critical path and project duration.

| Activity | Duration | Earliest Start (ES) | Latest Start (LS) | Earliest Finish (EF) | Latest Finish (LF) | Slack (LS-ES) | On the Critical Path? |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | 7 | 0 | 0 | 7 | 7 | 0-0=0 | Yes |
| B | 2 | 7 | 9 | 9 | 11 | 9-7=2 | No |
| C | 4 | 7 | 7 | 11 | 11 | 7-7=0 | Yes |
| D | 4 | 11 | 11 | 15 | 15 | 11-11=0 | Yes |
| E | 4 | 15 | 15 | 19 | 19 | 15-15=0 | Yes |
| F | 3 | 19 | 21 | 22 | 24 | 21-19=2 | No |
| G | 5 | 19 | 19 | 24 | 24 | 19-19=0 | Yes |

The critical path (bold path) is A-C-D-E-G with project duration of 24 days.

B

2

F

3

A

7

D

4

E

4

Start

Finish

C

4

G

5

- Analyze cost-time trade-offs

  - Total project costs

    - Direct costs

    - Indirect costs

  - Crashing (or expediting) cost

    - Normal time (NT)

    - Normal cost (NC)

Crash time (CT)

02-113

    - Crash cost (CC)		Crash cost per week = CC − NCNT − CT

  - Minimum-cost schedule

TEACHING TIP

As this is a complicated analysis, we do not suggest making this an application to be completed by the students in class. It is usually best to walk them through the procedure.

    - Step 1: determine the critical path

    - Step 2: find the activity (or activities) on the critical path(s) with the lowest cost of crashing

    - Step 3: reduce the time for this activity until

      - (a) it cannot be further reduced

      - (b) another path becomes critical

      - (c) the increase in direct costs exceeds the savings

    - Step 4: repeat this procedure until the increase in direct costs exceeds the savings

  - Use Application 2.3 (note: this problem is similar to problem 13, page 79-80)

| Project Activity and Cost Data (note: this is Table 2.6 from the Problems) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Normal Time (days) | Normal Cost ($) | Crash Time (days) | Crash Cost ($) | Immediate Predecessor(s) |
| A | 5 | 1,000 | 4 | 1,200 | -- |
| B | 5 | 800 | 3 | 2,000 | -- |
| C | 2 | 600 | 1 | 900 | A, B |
| D | 3 | 1,500 | 2 | 2,000 | B |
| E | 5 | 900 | 3 | 1,200 | C, D |
| F | 2 | 1,300 | 1 | 1,400 | E |
| G | 3 | 900 | 3 | 900 | E |
| H | 5 | 500 | 3 | 900 | G |

Indirect project costs= $250 per day and penalty cost = $100 per day for each day the project lasts beyond day 14.

02-114

Direct cost and time data for the activities:

|  |  | Maximum Crash |
| --- | --- | --- |
| Activity | Crash Cost/Day | Time (days) |
| A | 200 | 1 |
| B | 600 | 2 |
| C | 300 | 1 |
| D | 500 | 1 |
| E | 150 | 2 |
| F | 100 | 1 |
| G | 0 | 0 |
| H | 200 | 2 |

Solution:

Original costs:

Normal Total Costs = $7,500

Total Indirect Costs = $250 per day * 21 days = $5,250

Penalty Cost = $100 per day * 7 days = $700

Total Project Costs = $13,450

STAGE 1

Step 1: The critical path is B–D–E–G–H, and the project duration is 21 days.

Step 2: Activity E on the critical path has the lowest cost of crashing ($150 per day).  Note that activity G cannot be crashed.

Step 3: Reduce the time (crashing 2 days will reduce the project duration to 19 days) and re-calculate costs:

Costs Last Trial = $7,500

Crash Cost Added = $150 * 2 days = $300

Total Indirect Costs = $250 per day * 19 days = $4,750

Penalty Cost = $100 per day * 5 days = $500

Total Project Costs = $13,050

Note that the cost to crash ($250 per day) is less than the combined indirect cost and the penalty cost per day savings ($350).

Step 4: repeat this procedure until direct costs are greater than or equal to savings

02-115

STAGE 2

(step 1) the critical path is B–D–E–G–H, and the project duration is 19 days.

(step 2) Activity H on the critical path has the next lowest crashing cost ($200 per day).

(step 3) Reduce the time (crashing 2 days will reduce the project duration to 17 days) and re-calculate costs.

Costs Last Trial = $7,500 + $300 (the added crash cost) = $7,800

Crash Cost Added = $200 * 2 days = $400

Total Indirect Costs = $250 per day * 17 days = $4,250

Penalty Cost = $100 per day * 3 days = $300

Total Project Costs = $12,750

Note that the cost to crash ($200 per day) is less than the combined indirect cost and the penalty cost per day savings ($350).

(step 4):repeat the procedure

STAGE 3

(step 1) the critical path is B–D–E–G–H, and the project duration is 17 days.

(step 2) Activity D on the critical path has the next lowest crashing cost ($500 per day).

(step 3) Reduce the time (crashing 1 day will reduce the project duration to 16 days) and re-calculate costs.

Costs Last Trial = $7,800 + $400 (the added crash cost) = $8,200

Crash Cost Added = $500 * 1 day = $500

Total Indirect Costs = $250 per day * 16 days = $4,000

Penalty Cost = $100 per day * 2 days = $200

Total Project Costs = $12,900, which is greater than the last trial.

(step 4) We stop the crashing process and accept the solution from STAGE 2. Note that the cost to crash ($500 per day) is greater than the combined indirect cost and the penalty cost per day savings ($350).

A summary of the cost analysis follows. The recommended completion date is day 17 by crashing activity E by 2 days and activity H by 2 days.

|  |  | Resulting | Reduc- | Project | Costs | Crash | Total | Total | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Crash | Critical | tion | Duration | Last | Cost | Indirect | Penalty | Project |
| Trial | Activity | Paths | (days) | (days) | Trial | Added | Costs | Costs | Costs |
| 0 | — | B–D–E–G–H | — | 21 | $7,500 | — | $5,250 | $700 | $13,450 |
| 1 | E | B–D–E–G–H | 2 | 19 | $7,500 | $300 | $4,750 | $500 | $13,050 |
| 2 | H | B–D–E–G–H | 2 | 17 | $7,800 | $400 | $4,250 | $300 | $12,750 |

Further reductions will cost more than the savings in indirect costs and penalties.

The critical path is B–D–E–G–H.

Use Example 2.3: Find a Minimum-Cost Schedule

02-116

  - Active Model 2.2 in myomlab provides additional insight on cost analysis for the St. John’s Hospital project (example 2.1).

- Assessing risks

TEACHING TIP

Mention Managerial Practice 2.1:  “Boston’s Big Dig Project Poses Many Challenges” (1) massive highway tunnel built under the city of Boston, (2) it was completed late, over budget, and did not meet specification

  - Risk is the measure of the probability and consequence of not reaching a defined project goal and involves the notion of uncertainty as it relates to project timing and costs.

    - Risk-management plans

      - Strategic fit

      - Service/project attributes

      - Project team capability

      - Operations

    - Simulation

      - Using PERT/CPM to quantify risks

TEACHING TIP

To incorporate uncertainty into the network model, probability distribution can be calculated using two approaches:  computer simulation (see Supplement B “Simulation”) and statistical analysis

    - Statistical analysis

      - Optimistic time (a): shortest time an activity can be completed

      - Most likely time (m): best estimate of probable time

      - Pessimistic time (b): longest time an activity can take

    - Analysis

      - Activity’s mean time (te) and variance (2) with beta distribution

te=a+4m+b6

σ2=b−a62

  - Use Example 2.4: Calculating Means and Variance

Use Application 2.4 (note: this is problem 11)

02-117

Bluebird University: activity for sales training seminar. The bold-faced items represent the activities on the critical path.

A

D

G

J

B

E

Finish

I

Start

C

F

H

| Activity | Immediate Predecessor(s) | Optimistic (a) | Most Likely (m) | Pessimistic (b) | Expected Time (te) | Variance () |
| --- | --- | --- | --- | --- | --- | --- |
| A | -- | 5 | 7 | 8 | 6.83 | 0.25 |
| B | -- | 6 | 8 | 12 | 8.33 | 1.00 |
| C | -- | 3 | 4 | 5 | 4.00 | 0.11 |
| D | A | 11 | 17 | 25 | 17.33 | 5.44 |
| E | B | 8 | 10 | 12 | 10.00 | 0.44 |
| F | C, E | 3 | 4 | 5 | 4.00 | 0.11 |
| G | D | 4 | 8 | 9 | 7.50 | 0.69 |
| H | F | 5 | 7 | 9 | 7.00 | 0.44 |
| I | G, H | 8 | 11 | 17 | 11.50 | 2.25 |
| J | G | 4 | 4 | 4 | 4.00 | 0.00 |

Analyzing probabilities

02-118

Using the z-transformation formula:

Z=T−TEs2

where:

T	= due date of project

TE	= earliest expected completion date

s2	= sum of variances on the critical path

  - Near-critical paths

  - Use Example 2.5: Calculating the Probability of Completing a Project by a Given Date

  - Use Application 2.5 (note: this is problem 11)

The director of the continuing education at Bluebird University wants to conduct the seminar in 47 working days from now.  What is the probability that everything will be ready in time?

The critical path is A–D–G–I, and the expected completion time is 43.16 days.

T = 47 days, TE = 43.16 days, and the sum of the variances for the critical activities is: (0.25 + 5.44 + 0.69 + 2.25) = 8.63.

Assuming the normal distribution applies, we use the table for the normal probability distribution. Given z = 1.31, the probability that activities A–D–G–I can be completed in 47 days or less is 0.9049.

  - Active Model 2.3 in myomlab provides additional insight on probability analysis for the St. John’s Hospital project (example 2.1).

D. Monitoring and Controlling Projects

- Monitoring project status

  - Open issues and Risks

  - Schedule status

- Monitoring project resources

  - Project life-cycle: four major phases

    - Definition and organization

    - Planning

    - Execution

    - Close out

TEACHING TIP

02-119

Most resources are consumed in the execution phase

  - Options for managing and alleviating resource problems

    - Resource leveling

    - Resource allocation

    - Resource acquisition

- Controlling projects

  - Project managers have the responsibility of accounting for the effective use of the firm’s resources as well as managing activities to achieve the time and quality goals of the project

  - Projects provide a rich environment for developing future leaders

  - Close out

  - Write final reports

  - Complete remaining deliverables

  - Compile recommendations for improving project processes