## Model
Office LAN project - finding project time and critical path
Data on activity network
Activity | Label | Predecessors | Successors | Duration
Dummy Start node | Start | None | A | 0
Perform needs analysis | A | Start | B | 10
Develop specifications | B | A | C,D | 6
Select server | C | B | E,G | 6
Select software | D | B | F,G | 12
Select cables | E | C | F | 4
Purchase equipment | F | D,E | H,I | 3
Develop user manuals | G | C,D | J | 6
Wire offices | H | F | L | 12
Set up server | I | F | K | 3
Develop training program | J | G | M | 14
Install software | K | I | L | 4
Connect network | L | H,K | M,N | 3
Train users | M | J,L | O | 8
Test & debug system | N | L | O | 12
Get management acceptance | O | M,N | Finish | 4
Dummy Finish node | Finish | O | None | 0
Activity start and finish times
Activity | Earliest start time | Earliest finish time | Latest start time | Latest finish time | Slack
Start | 0 | 0 | 0 | 0
A | 0 | 10 | 0 | 10 | 0
B | 10 | 16 | 10 | 16 | 0
C | 16 | 22 | 18 | 24 | 2
D | 16 | 28 | 16 | 28 | 0
E | 22 | 26 | 24 | 28 | 2
F | 28 | 31 | 28 | 31 | 0
G | 28 | 34 | 30 | 36 | 2
H | 31 | 43 | 31 | 43 | 0
I | 31 | 34 | 36 | 39 | 5
J | 34 | 48 | 36 | 50 | 2
K | 34 | 38 | 39 | 43 | 5
L | 43 | 46 | 43 | 46 | 0
M | 48 | 56 | 50 | 58 | 2
N | 46 | 58 | 46 | 58 | 0
O | 58 | 62 | 58 | 62 | 0
Finish | 62 | 62 | 62 | 62
Project completion time | 62
Data for Gantt chart
Activity | Start time | Duration
Perform needs analysis | 0 | 10
Develop specifications | 0 | 6
Select server | 10 | 6
Select software | 16.5422 | 12
Select cables | 16 | 4
Purchase equipment | 23.7891 | 3
Develop user manuals | 28 | 6
Wire offices | 28.5993 | 12
Set up server | 31 | 3
Develop training program | 32.8598 | 14
Install software | 34.3638 | 4
Connect network | 37.1282 | 3
Train users | 43 | 8
Test & debug system | 48.3857 | 12
Get management acceptance | 46 | 4
Activities with 0 slack are on critical, i.e., they are on the critical path. Therefore, the critical path is A-B-D-F-H-L-N-O. The durations of the noncritical activities, C, E, G, I, J, K, and M, could be increased slightly without affecting the project completion time.
The noncritical activities can have start times anywhere within their earliest to latest start time ranges. There is no such flexibility for the critical activities.
Note on B24: 0 for Start node, for all others is equal to maximum earliest finish time, where maximum is over all predecessors
Note on C24: Earliest start time plus duration
Note on D24: Latest finish time minus duration
Note on E24: Equal to project time for Finish node; for others, equal to minimum of latest start times, where minimum is over all successors
Note on F24: Latest start time minus earliest start time. Equivalently, latest finish time minus earliest finish time

## SolverTableSheet (hidden)
1
$D$45
1
45
62
1
$B$47
$A$51