## Model
Office LAN project - finding project time and critical path
Data on activity network
Activity | Label | Predecessors | Successors | Duration | Start time
Dummy Start node | Start | None | A | 0 | 0
Perform needs analysis | A | Start | B | 10 | 0
Develop specifications | B | A | C,D | 6 | 10
Select server | C | B | E,G | 6 | 18
Select software | D | B | F,G | 12 | 16
Select cables | E | C | F | 4 | 24
Purchase equipment | F | D,E | H,I | 3 | 28
Develop user manuals | G | C,D | J | 6 | 28
Wire offices | H | F | L | 12 | 31
Set up server | I | F | K | 3 | 36
Develop training program | J | G | M | 14 | 34
Install software | K | I | L | 4 | 39
Connect network | L | H,K | M,N | 3 | 43
Train users | M | J,L | O | 8 | 50
Test & debug system | N | L | O | 12 | 46
Get management acceptance | O | M,N | Finish | 4 | 58
Dummy Finish node | Finish | O | None | 0 | 62 | Project completion time, same as before
Arcs in network
Origin node | Destination node | Diff in start times |  | Duration of origin
Start | A | 0 | >= | 0
A | B | 10 | >= | 10
B | C | 8 | >= | 6
B | D | 6 | >= | 6
C | E | 6 | >= | 6
C | G | 10 | >= | 6
D | F | 12 | >= | 12
D | G | 12 | >= | 12
E | F | 4 | >= | 4
F | H | 3 | >= | 3
F | I | 8 | >= | 3
G | J | 6 | >= | 6
H | L | 12 | >= | 12
I | K | 3 | >= | 3
J | M | 16 | >= | 14
K | L | 4 | >= | 4
L | M | 7 | >= | 3
L | N | 3 | >= | 3
M | O | 8 | >= | 8
N | O | 12 | >= | 12
O | Finish | 4 | >= | 4
It might be possible to see from this output which activities are critical (from binding and nonbinding constraints), but it's more difficult than before, where we could see the slacks directly.

## SolverTableSheet (hidden)
1
$D$45
1
45
62
1
$B$47
$A$51