## Model
Scheduling multiple (overlapping) projects
Workers available per month | 220
Project | Workers/month | Months | Revenue | Due date |  | Start |  | Upper bound | Finish | Earned
1 | 74 | 5 | 4800 | 5 |  | 6 | <= | 6 | 10 | 0
2 | 98 | 2 | 3330 | 6 |  | 7 | <= | 7 | 8 | 0
3 | 91 | 3 | 4100 | 7 |  | 8 | <= | 8 | 10 | 0
4 | 95 | 4 | 6840 | 8 |  | 4 | <= | 9 | 7 | 6840
5 | 59 | 2 | 1650 | 9 |  | 6 | <= | 10 | 7 | 1650
6 | 81 | 3 | 3880 | 8 |  | 1 | <= | 9 | 3 | 3880
7 | 84 | 4 | 6380 | 6 |  | 7 | <= | 7 | 10 | 0
8 | 78 | 3 | 4200 | 5 |  | 1 | <= | 6 | 3 | 4200
9 | 95 | 3 | 4860 | 6 |  | 7 | <= | 7 | 9 | 0
10 | 58 | 5 | 5220 | 5 |  | 1 | <= | 6 | 5 | 5220
Projects (along side) worked on in various months (along top)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
6 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Workers used | 217 | 217 | 217 | 153 | 153 | 154 | 154 | 0 | 0
Worker capacity exceeded? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total revenue earned | 21790
Penalty for exceeding capacity | 0
Objective to maximize | 21790
This is the best solution I could find by letting Evolutionary Solver run a long time, but it's possible that there's a somewhat better one. Note that the formulas in the rows 19-28 need an extra condition to account for the fact that the individual project deadlines differ.
Note on E5: For example, the revenue from project 1 is obtained only if project 1 is completed by the end of month 5.
Note on G5: The project will start at the beginning of this month.
Note on I5: If the start time equals this upper bound, it means the project isn't done at all.
Note on J5: The project will finish at the end of this month.