## Model
Office LAN project - simulation with random activity times
Data on activity network |  |  |  | Parameters of PERT distributions
Activity | Label | Predecessors | Successors | Min | Most likely | Max | Implied mean | Duration
Dummy Start node | Start | None | A |  |  |  |  | 0
Perform needs analysis | A | Start | B | 4 | 11 | 12 | 10 | #NAME?
Develop specifications | B | A | C,D | 2 | 6 | 10 | 6 | #NAME?
Select server | C | B | E,G | 5 | 6 | 7 | 6 | #NAME?
Select software | D | B | F,G | 4 | 13 | 16 | 12 | #NAME?
Select cables | E | C | F | 3 | 4 | 5 | 4 | #NAME?
Purchase equipment | F | D,E | H,I | 2 | 3 | 4 | 3 | #NAME?
Develop user manuals | G | C,D | J | 4 | 6 | 8 | 6 | #NAME?
Wire offices | H | F | L | 6 | 13 | 14 | 12 | #NAME?
Set up server | I | F | K | 3 | 3 | 3 | 3 | #NAME?
Develop training program | J | G | M | 12 | 14 | 16 | 14 | #NAME?
Install software | K | I | L | 3 | 4 | 5 | 4 | #NAME?
Connect network | L | H,K | M,N | 2 | 3 | 4 | 3 | #NAME?
Train users | M | J,L | O | 8 | 8 | 8 | 8 | #NAME?
Test & debug system | N | L | O | 10 | 12 | 14 | 12 | #NAME?
Get management acceptance | O | M,N | Finish | 3 | 4 | 5 | 4 | #NAME?
Dummy Finish node | Finish | O | None |  |  |  |  | 0
Activity start and finish times
Activity | Earliest start time | Earliest finish time | Latest start time | Latest finish time | Slack | On critical path? | Pr(critical)
Start | 0 | 0 | #NAME? | #NAME?
A | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
B | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
C | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
D | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
E | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
F | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
G | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
H | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
I | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
J | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
K | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
L | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
M | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
N | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
O | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Finish | #NAME? | #NAME? | #NAME? | #NAME?
Project completion time | #NAME?
The RiskMean values in column H might be meaningless until you rerun the simulation.
Many comparisons could be made, but this is one of the more extreme. The yellow rows were all very skewed to the right. I changed them so that they're skewed to the left or symmetric (but with the same means). See next two sheets for results.
Note on B24: 0 for Start node, for all others is equal to maximum earliest finish time, where maximum is over all predecessors
Note on C24: Earliest start time plus duration
Note on D24: Latest finish time minus duration
Note on E24: Equal to project time for Finish node; for others, equal to minimum of latest start times, where minimum is over all successors
Note on F24: Latest start time minus earliest start time. Equivalently, latest finish time minus earliest finish time

## Summary Report comparison
@RISK Summary Report
General Information
| Workbook Name | ProjectSimulation.xls
| Number of Simulations | 1
| Number of Iterations | 1000
| Number of Inputs | 15
| Number of Outputs | 1
| Sampling Type | Latin Hypercube
| Simulation Start Time | 2006-01-07 11:34
| Simulation Stop Time | 2006-01-07 11:34
| Simulation Duration | 0:00
| Random Seed | 1
| Total Errors | 0
Output and Input Summary Statistics
| Output Name | Output Cell | Simulation | Minimum | Maximum | Mean | Std Dev | x1 | p1 | x2 | p2 | x2-x1 | p2-p1 | Errors
| Project completion time | $B$43 | 1 | 52.5062 | 75.4034 | 62.7883 | 3.6085 | 57.1491 | 5% | 68.8425 | 95% | 11.6934 | 90% | 0
| Input Name | Input Cell | Simulation | Minimum | Maximum | Mean | Std Dev | x1 | p1 | x2 | p2 | x2-x1 | p2-p1 | Errors
| B / Duration | $I$6 | 1 | 8.0201 | 14.7398 | 9.9999 | 1.3097 | 8.2915 | 5% | 12.4972 | 95% | 4.2057 | 90% | 0
| C,D / Duration | $I$7 | 1 | 4.0061 | 10.5852 | 5.9997 | 1.3088 | 4.2882 | 5% | 8.4894 | 95% | 4.2012 | 90% | 0
| E,G / Duration | $I$8 | 1 | 5.0887 | 6.915 | 6 | 0.37807 | 5.3763 | 5% | 6.6206 | 95% | 1.2443 | 90% | 0
| F,G / Duration | $I$9 | 1 | 4.8646 | 15.924 | 11.9997 | 2.1405 | 8.1012 | 5% | 15.0809 | 95% | 6.9796 | 90% | 0
| F / Duration | $I$10 | 1 | 3.0583 | 4.9409 | 4 | 0.37833 | 3.3783 | 5% | 4.6209 | 95% | 1.2426 | 90% | 0
| H,I / Duration | $I$11 | 1 | 2.0541 | 3.931 | 2.9999 | 0.37818 | 2.3764 | 5% | 3.6203 | 95% | 1.2438 | 90% | 0
| J / Duration | $I$12 | 1 | 4.1479 | 7.8241 | 5.9999 | 0.75611 | 4.7529 | 5% | 7.2402 | 95% | 2.4872 | 90% | 0
| L / Duration | $I$13 | 1 | 10.0049 | 16.7814 | 11.9999 | 1.3096 | 10.29 | 5% | 14.4986 | 95% | 4.2087 | 90% | 0
| K / Duration | $I$14 | 1 | 3 | 3 | 3 | 0 | 3 | 5% | 3 | 95% | 0 | 90% | 0
| M / Duration | $I$15 | 1 | 12.125 | 15.812 | 14 | 0.75607 | 12.7525 | 5% | 15.241 | 95% | 2.4886 | 90% | 0
| L / Duration | $I$16 | 1 | 3.0429 | 4.9052 | 4 | 0.37811 | 3.3775 | 5% | 4.6213 | 95% | 1.2438 | 90% | 0
| M,N / Duration | $I$17 | 1 | 2.0795 | 3.9195 | 3 | 0.37811 | 2.3779 | 5% | 3.6201 | 95% | 1.2422 | 90% | 0
| O / Duration | $I$18 | 1 | 8 | 8 | 8 | 0 | 8 | 5% | 8 | 95% | 0 | 90% | 0
| O / Duration | $I$19 | 1 | 6.0702 | 20.9569 | 12.0001 | 2.93 | 7.6079 | 5% | 17.1828 | 95% | 9.5749 | 90% | 0
| Finish / Duration | $I$20 | 1 | 3.082 | 4.9239 | 4 | 0.37815 | 3.3759 | 5% | 4.62 | 95% | 1.2441 | 90% | 0
| Output Name | Output Cell | Simulation | Minimum | Maximum | Mean | Std Dev | x1 | p1 | x2 | p2 | x2-x1 | p2-p1 | Errors
| Project completion time | $B$43 | 1 | 52.8322 | 70.2889 | 62.4114 | 2.9966 | 57.2137 | 5% | 67.3298 | 95% | 10.1162 | 90% | 0
| Input Name | Input Cell | Simulation | Minimum | Maximum | Mean | Std Dev | x1 | p1 | x2 | p2 | x2-x1 | p2-p1 | Errors
| B / Duration | $I$6 | 1 | 5.4111 | 11.9856 | 10.0002 | 1.309 | 7.4968 | 5% | 11.707 | 95% | 4.2103 | 90% | 0
| C,D / Duration | $I$7 | 1 | 2.2049 | 9.6217 | 5.9998 | 1.5127 | 3.5047 | 5% | 8.4768 | 95% | 4.9722 | 90% | 0
| E,G / Duration | $I$8 | 1 | 5.0887 | 6.915 | 6 | 0.37807 | 5.3763 | 5% | 6.6206 | 95% | 1.2443 | 90% | 0
| F,G / Duration | $I$9 | 1 | 4.8646 | 15.924 | 11.9997 | 2.1405 | 8.1012 | 5% | 15.0809 | 95% | 6.9796 | 90% | 0
| F / Duration | $I$10 | 1 | 3.0583 | 4.9409 | 4 | 0.37833 | 3.3783 | 5% | 4.6209 | 95% | 1.2426 | 90% | 0
| H,I / Duration | $I$11 | 1 | 2.0541 | 3.931 | 2.9999 | 0.37818 | 2.3764 | 5% | 3.6203 | 95% | 1.2438 | 90% | 0
| J / Duration | $I$12 | 1 | 4.1479 | 7.8241 | 5.9999 | 0.75611 | 4.7529 | 5% | 7.2402 | 95% | 2.4872 | 90% | 0
| L / Duration | $I$13 | 1 | 6.876 | 13.987 | 11.9998 | 1.3109 | 9.4907 | 5% | 13.7074 | 95% | 4.2167 | 90% | 0
| K / Duration | $I$14 | 1 | 3 | 3 | 3 | 0 | 3 | 5% | 3 | 95% | 0 | 90% | 0
| M / Duration | $I$15 | 1 | 12.125 | 15.812 | 14 | 0.75607 | 12.7525 | 5% | 15.241 | 95% | 2.4886 | 90% | 0
| L / Duration | $I$16 | 1 | 3.0429 | 4.9052 | 4 | 0.37811 | 3.3775 | 5% | 4.6213 | 95% | 1.2438 | 90% | 0
| M,N / Duration | $I$17 | 1 | 2.0795 | 3.9195 | 3 | 0.37811 | 2.3779 | 5% | 3.6201 | 95% | 1.2422 | 90% | 0
| O / Duration | $I$18 | 1 | 8 | 8 | 8 | 0 | 8 | 5% | 8 | 95% | 0 | 90% | 0
| O / Duration | $I$19 | 1 | 10.0701 | 13.8874 | 12 | 0.75657 | 10.7553 | 5% | 13.2402 | 95% | 2.4849 | 90% | 0
| Finish / Duration | $I$20 | 1 | 3.082 | 4.9239 | 4 | 0.37815 | 3.3759 | 5% | 4.62 | 95% | 1.2441 | 90% | 0
The top results use the original inputs; the bottom results use the new inputs. In either case, the mean project length is greater than 62, the project length using the means of the inputs. Actually, this will always be the case in projects. The next sheet shows how the distribution of project length differs. It has a slightly different shape.

## Output Graphs comparison
@RISK Output Graphs
Simulation: 1 / Output: Project completion time
Original - inputs skewed to the right
New - inputs skewed to the left or symmetric