## Part a
New product introduction at Jiffyco
Activity data
Activity | Predecessors | Successors | Duration
Start | None | A,B | 0
A | Start | C | 6
B | Start | F | 5
C | A | D | 3
D | C | E | 2
E | D | G | 3
F | B | H | 4
G | E | H | 4
H | G,F | Finish | 2
Finish | H | None | 0
Activity start and finish times
Activity | Earliest start time | Earliest finish time | Latest finish time | Latest start time | Slack
Start | 0 | 0 | 0 | 0
A | 0 | 6 | 6 | 0 | 0
B | 0 | 5 | 14 | 9 | 9
C | 6 | 9 | 9 | 6 | 0
D | 9 | 11 | 11 | 9 | 0
E | 11 | 14 | 14 | 11 | 0
F | 5 | 9 | 18 | 14 | 9
G | 14 | 18 | 18 | 14 | 0
H | 18 | 20 | 20 | 18 | 0
Finish | 20 | 20 | 20 | 20
Project time | 20
Note on B18: 0 for Start node, for all others is equal to maximum earliest finish time, where maximum is over all predecessors
Note on C18: Earliest start time plus duration
Note on D18: Equal to project time for Finish node; for others, equal to minimum of latest start times, where minimum is over all successors
Note on E18: Latest finish time minus duration
Note on F18: Latest start time minus earliest start time. Equivalently, latest finish time minus earliest finish time
Start
A
B
C
D
F
E
G
H
Finish
Critical path is shown in red.

## Part b
New product introduction at Jiffyco - crashing
Activity data
Activity | Predecessors | Successors | Duration |  | Original | Crash |  | Maximum | Cost
Start | None | A,B | 0
A | Start | C | 6 |  | 6 | 0 | <= | 2 | 80
B | Start | F | 5 |  | 5 | 0 | <= | 2 | 60
C | A | D | 1 |  | 3 | 2 | <= | 2 | 30
D | C | E | 0 |  | 2 | 2 | <= | 2 | 60
E | D | G | 1 |  | 3 | 2 | <= | 2 | 40
F | B | H | 4 |  | 4 | 0 | <= | 2 | 30
G | E | H | 2 |  | 4 | 2 | <= | 2 | 20
H | G,F | Finish | 2
Finish | H | None | 0
Activity start and finish times
Activity | Earliest start time | Earliest finish time | Latest finish time | Latest start time | Slack
Start | 0 | 0 | 0 | 0
A | 0 | 6 | 6 | 0 | 0
B | 0 | 5 | 6 | 1 | 1
C | 6 | 7 | 7 | 6 | 0
D | 7 | 7 | 7 | 7 | 0
E | 7 | 8 | 8 | 7 | 0
F | 5 | 9 | 10 | 6 | 1
G | 8 | 10 | 10 | 8 | 0
H | 10 | 12 | 12 | 10 | 0
Finish | 12 | 12 | 12 | 12
Project time | 12 | <= | 12
Crashing cost | 300
Note on B18: 0 for Start node, for all others is equal to maximum earliest finish time, where maximum is over all predecessors
Note on C18: Earliest start time plus duration
Note on D18: Equal to project time for Finish node; for others, equal to minimum of latest start times, where minimum is over all successors
Note on E18: Latest finish time minus duration
Note on F18: Latest start time minus earliest start time. Equivalently, latest finish time minus earliest finish time