## Model
Expanding TV cable offerings
Activity information | [5 empty] | Data for Gantt chart
Description | Activity | Predecessors | Successors | Duration
| Start | None | A | 0 |  | Activity | Start time | Duration
Choose stations | A | None | B | 2 |  | Choose stations | 0 | 2
Get town council approval | B | A | C,D,F | 4 |  | Get town council approval | 2 | 4
Order converters | C | B | E | 3 |  | Order converters | 6 | 3
Install new dish | D | B | E | 2 |  | Install new dish | 6 | 2
Install converters | E | C,D | Finish | 10 |  | Install converters | 9 | 10
Change billing system | F | B | Finish | 4 |  | Change billing system | 12 | 4
| Finish | E,F | None | 0
Activity start and finish times
Activity | Earliest start time | Earliest finish time | Latest finish time | Latest start time | Slack
Start | 0 | 0 | 0 | 0
A | 0 | 2 | 2 | 0 | 0
B | 2 | 6 | 6 | 2 | 0
C | 6 | 9 | 9 | 6 | 0
D | 6 | 8 | 9 | 7 | 1
E | 9 | 19 | 19 | 9 | 0
F | 6 | 10 | 19 | 15 | 9
Finish | 19 | 19 | 19 | 19
Project completion time | 19
Note on B15: 0 for Start node, for all others is equal to maximum earliest finish time, where maximum is over all predecessors
Note on C15: Earliest start time plus duration
Note on D15: Equal to project time for Finish node; for others, equal to minimum of latest start times, where minimum is over all successors
Note on E15: Latest finish time minus duration
Note on F15: Latest start time minus earliest start time. Equivalently, latest finish time minus earliest finish time
The critical path is A-B-C-E.
Start
A
B
C
D
E
F
Finish