## Model
Building a new water treatment plant
Data on activities
Activity | Code | Predecessors | Successors | Mean | Stdev | Duration
Start | Start | None | D |  |  | 0
Design plant | D | Start | S,C,P | 6 | 1.5 | #NAME?
Select site | S | D | B | 2 | 0.3 | #NAME?
Select building contractor | C | D | W,M | 4 | 1 | #NAME?
Select operating personnel | P | D | T | 3 | 1 | #NAME?
Erect building | B | S | I | 24 | 6 | #NAME?
Order water treatment machine | W | C | I | 14 | 4 | #NAME?
Prepare operations manual | M | C | T | 3 | 0.4 | #NAME?
Train | T | P,M | L | 4 | 1 | #NAME?
Install treatment machine | I | B,W | L | 6 | 1 | #NAME?
Obtain operating license | L | I,T | Finish | 3 | 0.6 | #NAME?
Finish | Finish | L | None |  |  | 0
Activity start and finish times
Activity | Earliest start time | Earliest finish time | Latest finish time | Latest start time | Slack | Critical? | Pr(critical)
Start | 0 | 0 | #NAME? | #NAME?
D | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
S | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
C | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
P | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
B | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
W | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
M | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
T | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
I | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
L | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Finish | #NAME? | #NAME? | #NAME? | #NAME?
Project completion time | #NAME?
Complete within 50 days? | #NAME?
Complete after 55 days? | #NAME?
Start
D
S
C
P
B
W
M
T
I
L
Finish
According to the summary measures on the next sheet, the mean project completion time is about 41.5 days. The probability of completing in less than 50 days is 0.921, and the probability of completing in more than 55 days is 0.011. I found the probability of each activity being critical by using the RiskMean function on the 0-1 values in column G.
Note on B19: 0 for Start node, for all others is equal to maximum earliest finish time, where maximum is over all predecessors
Note on C19: Earliest start time plus duration
Note on D19: Equal to project time for Finish node; for others, equal to minimum of latest start times, where minimum is over all successors
Note on E19: Latest finish time minus duration
Note on F19: Latest start time minus earliest start time. Equivalently, latest finish time minus earliest finish time

## Summary Report
@RISK Summary Report
General Information
| Workbook Name | S10_08.xls
| Number of Simulations | 1
| Number of Iterations | 1000
| Number of Inputs | 10
| Number of Outputs | 3
| Sampling Type | Latin Hypercube
| Simulation Start Time | 2003-11-11 12:38
| Simulation Stop Time | 2003-11-11 12:38
| Simulation Duration | 0:00
| Random Seed | 1254531466
| Total Errors | 0
Output and Input Summary Statistics
| Output Name | Output Cell | Simulation | Minimum | Maximum | Mean | Std Dev | x1 | p1 | x2 | p2 | x2-x1 | p2-p1 | Errors
| Project time | $B$33 | 1 | 24.3546 | 62.5606 | 41.4988 | 5.8163 | 32.3123 | 5% | 51.472 | 95% | 19.1596 | 90% | 0
| Complete under 50 | $B$34 | 1 | 0 | 1 | 0.921 | 0.26987 | 0 | 5% | 1 | 95% | 1 | 90% | 0
| Complete over 55 | $B$35 | 1 | 0 | 1 | 0.011 | 0.10435 | 0 | 5% | 0 | 95% | 0 | 90% | 0
| Input Name | Input Cell | Simulation | Minimum | Maximum | Mean | Std Dev | x1 | p1 | x2 | p2 | x2-x1 | p2-p1 | Errors
| S,C,P / Duration | $G$6 | 1 | 1.3159 | 11.2237 | 6.0007 | 1.5006 | 3.5268 | 5% | 8.4625 | 95% | 4.9357 | 90% | 0
| B / Duration | $G$7 | 1 | 1.0112 | 2.9723 | 2 | 0.29996 | 1.5052 | 5% | 2.4917 | 95% | 0.98656 | 90% | 0
| W,M / Duration | $G$8 | 1 | 0.44781 | 7.4004 | 3.9999 | 1.0007 | 2.3476 | 5% | 5.6401 | 95% | 3.2925 | 90% | 0
| T / Duration | $G$9 | 1 | -0.3783 | 7.3148 | 3.0008 | 1.004 | 1.3527 | 5% | 4.6401 | 95% | 3.2874 | 90% | 0
| I / Duration | $G$10 | 1 | 2.2011 | 44.9792 | 24.0005 | 6.0078 | 14.1108 | 5% | 33.8147 | 95% | 19.7039 | 90% | 0
| I / Duration | $G$11 | 1 | 0.20681 | 28.1662 | 14.0007 | 4.0058 | 7.3897 | 5% | 20.5451 | 95% | 13.1554 | 90% | 0
| T / Duration | $G$12 | 1 | 1.6947 | 4.328 | 2.9999 | 0.39972 | 2.3383 | 5% | 3.6579 | 95% | 1.3196 | 90% | 0
| L / Duration | $G$13 | 1 | 0.61471 | 7.5018 | 4.0002 | 1.0006 | 2.348 | 5% | 5.6362 | 95% | 3.2882 | 90% | 0
| L / Duration | $G$14 | 1 | 2.7543 | 9.1491 | 5.9996 | 0.99923 | 4.3505 | 5% | 7.6408 | 95% | 3.2903 | 90% | 0
| Finish / Duration | $G$15 | 1 | 0.71787 | 5.0124 | 2.9997 | 0.60125 | 2.0074 | 5% | 3.9835 | 95% | 1.9761 | 90% | 0

## Output Graphs
@RISK Output Graphs
Simulation: 1 / Output: Project time
Simulation: 1 / Output: Complete under 50
Simulation: 1 / Output: Complete over 55