## RiskSerializationData (hidden)
1 | 0
0
10 | TRUE | 0 | 1 | GF1_rK0qDwEADADDAAwjACYAOwBRAGUAZgByAH4AnQC/ALkAKgD//wAAAAAAAQQAAAAAB0dlbmVyYWwAAAABEEJhdGNoZXMgcmVxdWlyZWQBAAEBEAACAAEKU3RhdGlzdGljcwMBAQD/AQEBAQEAAQEBAAIAAQEBAQEAAQEBAAIAAYIAAhcAEEJhdGNoZXMgcmVxdWlyZWQAAC8BAgACAKUArwABAQIBmpmZmZmZqT8AAGZmZmZmZu4/AAAFAAEBAQABAQEA | 1 | 0 | 0 | >75% | <25% | >90% | 10 | 1 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
0
FALSE | 13440 | 6498 | 10560 | 100
FALSE | 13440 | 6497.5 | 10560 | 500
FALSE | 13440 | 6497.5 | 10560 | 1000
FALSE | 13440 | 6497.5 | 10560 | 1500
FALSE | 13440 | 6497.5 | 10560 | 2000
0
0.01 | FALSE | FALSE | 10 | 0.5 | 1

## Model
Planning production of a drug
Input section
Ounces required | 8000 |  |  |  | Distribution of days needed to produce a batch (discrete)
Due date | 2013-12-01 |  |  |  |  | Days | Probability
[6 empty] | 5 | 0.05
Distribution of yield (ounces) from each batch (triangular) | [5 empty] | 6 | 0.1
| Min | Most likely | Max |  |  | 7 | 0.2
| 600 | 1000 | 1100 |  |  | 8 | 0.3
[6 empty] | 9 | 0.2
Prob of passing inspection | 0.6 |  |  |  |  | 10 | 0.1
Possible values | 0.6 | 0.7 | 0.8 | 0.9 | 1 | 11 | 0.05
Simulation model | [6 empty] | Outputs
Batch | Days | Yield | Pass? | CumYield | Enough? |  | Batches required | 10
1 | 8 | 900 | Yes | 900 | No |  | Days to complete | 80
2 | 8 | 900 | Yes | 1800 | No |  | Day to start | 2013-09-12
3 | 8 | 900 | Yes | 2700 | No
4 | 8 | 900 | Yes | 3600 | No
5 | 8 | 900 | Yes | 4500 | No
6 | 8 | 900 | Yes | 5400 | No
7 | 8 | 900 | Yes | 6300 | No
8 | 8 | 900 | No | 6300 | No
9 | 8 | 900 | Yes | 7200 | No
10 | 8 | 900 | Yes | 8100 | Yes
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Note: You will see errors in cells unless @RISK is loaded.
It turns out that for a low probability in cell B11, there were sometimes more than 25 batches, so I increased the potential number of batches to 40 (copied the logic down) just to be safe. The next sheet indicates how the outputs are affected by the probability of passing inspection. In particular, the 95th percentile of the number of days required to complete the order decreases dramatically as the probability of passing inspection increases.

## Output Results
@RISK Output Results
Performed By: Chris
Date: Saturday, March 15, 2014 12:44:16 PM
Name | Cell | Sim# | Graph | Min | Mean | Max | Std Dev | 5% | 95%
Batches required | I15 | 1 |  | 9 | 15.6356 | 25 | 3.2692 | 11 | 22
Batches required | I15 | 2 |  | 9 | 13.5926 | 24 | 2.5738 | 10 | 18
Batches required | I15 | 3 |  | 9 | 11.73 | 19 | 1.8484 | 9 | 15
Batches required | I15 | 4 |  | 9 | 10.466 | 17 | 1.2484 | 9 | 13
Batches required | I15 | 5 |  | 9 | 9.374 | 11 | 0.48822 | 9 | 10
Days to complete | I16 | 1 |  | 68 | 126.174 | 247 | 28.32 | 86 | 179
Days to complete | I16 | 2 |  | 62 | 108.83 | 208 | 21.3896 | 78 | 146
Days to complete | I16 | 3 |  | 59 | 93.928 | 159 | 15.8815 | 72 | 124
Days to complete | I16 | 4 |  | 62 | 83.706 | 137 | 11.0635 | 68 | 105
Days to complete | I16 | 5 |  | 59 | 74.976 | 95 | 6.0589 | 66 | 86