## Model
Scheduling multiple (overlapping) projects
Deadline | 10
Workers available per month | 220
Project | Workers/month | Months | Revenue |  | Start | Finish | Earned
1 | 74 | 5 | 4800 |  | 11 | 15 | 0
2 | 98 | 2 | 3330 |  | 5 | 6 | 13320
3 | 91 | 3 | 4100 |  | 1 | 3 | 28700
4 | 95 | 4 | 6840 |  | 1 | 4 | 41040
5 | 59 | 2 | 1650 |  | 7 | 8 | 3300
6 | 81 | 3 | 3880 |  | 7 | 9 | 3880
7 | 84 | 4 | 6380 |  | 11 | 14 | 0
8 | 78 | 3 | 4200 |  | 7 | 9 | 4200
9 | 95 | 3 | 4860 |  | 4 | 6 | 19440
10 | 58 | 5 | 5220 |  | 10 | 14 | 0
Projects (along side) worked on in various months (along top)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
9 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Workers used | 186 | 186 | 186 | 190 | 193 | 193 | 218 | 218 | 159 | 58
Worker capacity exceeded? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total revenue earned | 113880
Penalty for exceeding capacity | 0
Objective to maximize | 113880
The only change required is in the Earned formulas in column H. I got tired of waiting for Evolutionary Solver, so I stopped it at this solution. You might find a slightly better solution.
Note on F6: The project will start at the beginning of this month.
Note on G6: The project will finish at the end of this month.