CHAPTER 2

- Give three examples of business needs for a system.

- Maintain or improve the competitive position

- Perform a business function more efficiently

- Take advantage of a new business opportunity

- What is the purpose of an approval committee? Who is usually on this committee?

The approval committee generally serves as the decision making body regarding business investments in information systems projects. This approval committee could be a company steering committee that meets regularly to make information systems decisions, a senior executive who has control of organizational resources, or any other decision-making body that governs the use of business investments.

This committee generally has a broad organizational representation, and therefore can avoid allocating resources that will serve only narrow organizational interests. The approval committee commonly has project oversight responsibilities as well as monitoring project performance after the project has been accepted.

- Why should the system request be created by a businessperson as opposed to an IS professional?

It is important to have a clear understanding of how system will improve business. Companies have now realized that identifying business value and understanding the risks associated with the project are necessary to avoid any potential risks involved. Usually the system originates with a businessperson as he understands the need for the system or system improvement in the business unit and will have a much better idea of the value of the proposed system or improvement and therefore is in a better position to create a meaningful system request

In fact, the ideal situation is for both IT people (i.e., the experts in systems) and the business people (i.e., the experts in business) to work closely to find ways for technology to support business needs. In this way, organizations can leverage the exciting technologies that are available while ensuring that projects are based upon real business objectives, such as increasing sales, improving customer service, and decreasing operating expenses.

- What is the difference between intangible value and tangible value? Give three examples of each.

Tangible Value: Tangible value can be quantified and measured easily. Tangible value represents the benefits from the systems that are quantifiable and measurable.

Example: (a) increased sales (b) reduced operating costs (c) reduced interest costs etc…

Intangible Value: An intangible value results from an intuitive belief that the system provides important, but hard-to-measure benefits to the organization. Intangible value represents benefits that are real, but are difficult to quantify and measure.

Example: (a) increased customer satisfaction (b) improved decision making (c) better competitive positioning, etc.

- What are the purposes of the system request and the feasibility analysis? How are they used in the project selection process?

The purpose of the system request is to initiate a systems project. A system request is a document that describes the business reasons for building a system and the value that the system is expected to provide.

The project sponsor usually completes this form as part of a formal system project selection process within the organization. Most system requests include five elements: project sponsor, business need, business requirements, business value, and special issues

The feasibility analysis represents a more detailed investigation into the proposed system outlined in the system request. Feasibility analysis guides the organization in determining whether to proceed with a project. Feasibility analysis also identifies the important risks associated with the project that must be addressed if the project is approved.

The system analyst and the project sponsor work together to more fully develop the objectives of the system and to understand its potential costs and benefits to the organization.

The system request and the feasibility analysis are the key inputs used by the approval committee in determining if the proposed system has enough merit to move into the Analysis Phase.

- Describe two special issues that may be important to list on a system request.

Environmental factors should be considered (e.g., new governmental reporting requirements); competitive factors (e.g., IS-enabled systems introduced or anticipated by competitors); externally imposed deadlines that cannot be altered (e.g., completion by the start of the next fiscal year); and mandated technologies (e.g., including wireless access).

- Describe the three techniques for feasibility analysis.

Every organization has its own process and format for the feasibility analysis, but most include three techniques:

  - Technical feasibility:  Technical feasibility looks at the capability of the organization to successfully develop the proposed system.  Included in this assessment is the project size, the types of technologies to be used in the project, and the amount of prior experience with that technology and the business application.

  - Economic feasibility:  Economic feasibility addresses the economic justification of the project. Here, we attempt to determine if the value of the project's benefits justifies investing in the project's estimated costs.

  - Organizational feasibility:  Organizational feasibility evaluates whether the system is likely to be accepted and used by the organization. Included in this assessment will be the strength of the sponsor's and management's support for the project and the enthusiasm or resistance of the users for the project.

- Describe a “risky” project in terms of technical feasibility. Describe a project that would not be considered “risky.”

A project that would be technically risky would be one that is large in scale, utilizes technology that we have little or no experience with, and is for a business area that is new and unfamiliar to the organization.

A project that would not be considered technically risky would be one that is small in scale, uses technology that is well understood, and is for a business area that is very familiar to the users and developers.

- What are the steps for assessing economic feasibility? Describe each step.

The four steps for assessing economic feasibility are:

  - Identify costs and benefits of the proposed system.

  - Assign values to the costs and benefits.

  - Determine the cash flow of the project over the analysis period.

  - Determine the project's investment return.

- List two intangible benefits. Describe how these benefits can be quantified.

- One example of an intangible benefit is reduced response time to customer requests. Estimating the increase in the number of customers that could be served and the average revenue gained per customer could approximate the value of this benefit.  So, if we currently have 1000 customers, the average revenue per customer is $100, and by reducing our response time we can increase the number of customers served by 30%, then our benefit will be $30,000 (300 add'l customers @ $100).  (Note: this analysis assumes that demand for the product will increase with our increased capacity.  If demand remains constant, however, reduced response time will allow us to save money due to less frequent overtime; allow for greater flexibility in absorbing urgent projects; or create other similar value, though the economic impact of these may be more difficult to estimate).

- A second example of an intangible benefit is improved customer satisfaction. Determining how much repeat business we lose from dissatisfied customers could approximate the value of this benefit. The amount of repeat business lost could be estimated through customer satisfaction surveys or marketing research.  Assume we currently have 1000 customers, each customer brings in average revenue of $100, and we currently lose the repeat business of 10% of our customers due to dissatisfaction. If an improvement in customer satisfaction resulted in losing only 5% of repeat business, then the value of that benefit would be $5,000 (50 customers retained @$100).

- List two tangible benefits and two operational costs for a system. How would you       determine the values that should be assigned to each item?

Two tangible benefits are: an increase in sales and a decrease in uncollectible accounts receivable. The best way to measure these benefits is to go to the business people who understand these areas and ask them for reasonable estimates. The sales and marketing managers and the accounts receivable managers will be in the best position to determine these values.

Operational costs are the ongoing costs associated with the new system, and are fairly easy to determine objectively. One common operational cost is that of maintenance agreements for new hardware, which can be determined by contacting hardware vendors about the costs of their maintenance contracts. Another common operations cost is that of new employees that will be needed to run the new system. Salaries and benefits for new employees can be determined by checking local and regional salary and wage surveys for the type of employee needed.

- Explain the net present value and return on investment for a cost–benefit analysis.  Why would these calculations be used?

Net Present Value:  The net present value (NPV) method compares the present values of the project's cash inflows and outflows. If the present value of the benefits (inflows) is equal to or greater than the present value of the costs (outflows), then the project is considered economically justifiable. NPV has the advantage of including a required rate of return in the calculation, so the NPV figure captures the costs associated with tying up money in the project. NPV also explicitly considers the timing of the cash flows throughout the system life.

Return on Investment:  The return on investment (ROI) method simply compares the total net cash flows from the project with the total outflows in aggregate. While this ROI number gives some sense of how much money the project generates in comparison to its total cost, it omits any consideration of the timing of the cash flows and the time value of money. The ROI method, while simple to compute, is flawed in many ways and should not be used as the only economic indicator of a project's merit.

- What is the break-even point for the project? How is it calculated?

Break-even point is defined as the point in time at which the costs of the project equal the value it has delivered. It is determined by looking at the cash flow over time and identifying the year in which the benefits are greater than the costs.

In a project situation, if the project team needs to perform a rigorous cost–benefit analysis, they need to include information about the length of time before the project will break-even, or when the returns will match the amount invested in the project. The greater the time it takes to break-even, the riskier the project.

- What is stakeholder analysis? Discuss three stakeholders that would be relevant        for most projects.

Stakeholder analysis is a systematic process that identifies all parties that will be affected by a new information system, and attempts to estimate the consequences of the project for each stakeholder group. A major goal of stakeholder analysis is to ensure that the consequences of a new system are considered for all parties that will be affected by the system.

The most common stakeholders to consider for most systems projects are:

- The system champion: The system champion is the person or group who initiates the project and provides support for it.

- The system users: The users are the individuals who will work with the system once it is implemented.

- The organization's management: The organization management commits resources to the project and has an interest in seeing those resources be used to improve the functioning of the organization.

- Why do many projects end up having unreasonable deadlines? How should a project manager react to unreasonable demands?

Unreasonable deadlines are often the consequence of trying to complete the project to accomplish some business goal rather than being based on a realistic assessment of how long the project will actually take to complete. For example, in the CD Selections case, the project sponsor wants the Internet marketing system to be operational in time to sell CDs for holiday shopping. Too often such external factors are used to create target dates for project completion. The project manager must develop accurate and realistic time estimates for the project, and use these to convince the sponsor that his/her timelines can't be achieved. The project manager is setting the project team up to fail if he/she goes along with a time frame that is known to be unachievable. If the time deadline is immovable, then the project manager should employ time boxing to negotiate a narrowed project scope that will be achievable in the time allotted.

- What is the trade-offs that project managers must manage?

The science (or art) of project management is in making trade-offs among three important concepts:

- The size of the system (in terms of what it does)

- The time to complete the project (when the project will be finished)

- The cost of the project.

A larger project will require more time and money; while a short time frame may require more money or reduced project size. Since most projects have time and/or money constraints, the project manager must strike a balance between size, time, and cost in order to define an achievable project.

- Compare and contrast the Gantt chart and the network diagram.

- Gantt Chart: In the Gantt chart, horizontal bars are drawn to represent the duration of each task, and as people work on tasks, the appropriate bars are filled in proportionately to how much of the task is finished. Creating a Gantt chart is simple and can be done using a spreadsheet package, graphics software (e.g., Microsoft VISIO), or a project management package.

- Network Diagram: PERT, which stands for Program Evaluation and Review Technique, is a network analysis technique that can be used when the individual task time estimates are fairly uncertain. Instead of simply putting a point estimate for the duration estimate, PERT uses three time estimates: optimistic, most likely, and a pessimistic. It then combines the three estimates into a single weighted average estimate using the following formula:

PERT weighted average =

optimistic estimate + (4 × most likely estimate) + pessimistic estimate

------------------------------------------------------------------------------------

6

The PERT chart is drawn as a node and arc type of graph that shows the time estimates in the nodes and the task dependencies on the arcs. Each node represents an individual task, and a line connecting two nodes represents the dependency between two tasks. Pert Chart is the best way to communicate task dependencies because they lay out the tasks as a flowchart in the order in which they need to be completed. The longest path from the project inception to completion is referred to as the critical path.

- Some companies hire consulting firms to develop the initial project plans and manage the project, but use their own analysts and programmers to develop the system. Why do you think some companies do this?

Clearly, the tasks involved in initial project plans and managing the project differ from those involved in the technical development of new systems.  Firms may wish to take advantage of the expertise of outside firms in this aspect of development.  Other companies do the opposite.  They use their own staff to initiate and manage projects but hire consultants, temporary personnel, or outsourcing firms to do the actual programming

- What is a use-case point? For what is it used?

Use-case points is a use cases based project effort estimation approach, which was originally developed based on unique features of use cases and object orientation. From a practical point of view, to estimate effort using use-case points, the use cases and the use-case diagram must have been created.

- What process do we use to estimate systems development based on use cases?

Use case models have two primary constructs: actors and use cases. For use-case point estimation purposes, actors can be classified as simple, average, or complex. Simple actors are separate systems with which the current system must communicate through a well-defined application program interface (API). Average actors are separate systems that interact with the current system using standard communication protocols, such as TCP/IP, FTP, or HTTP, or an external database that can be accessed using standard SQL. Complex actors are typically end users communicating with the system. Once all of the actors have been categorized as being simple, average, or complex, the project manager will count the number of actors in each category and enter the values into the unadjusted actor weighting table contained in the use case point–estimation worksheet. The project manager will then compute the Unadjusted Actor Weight Total (UAW). This is computed by summing the individual results that were computed by multiplying the weighting factor by the number of actors of each type.

A use case represents a major business process that the system will perform that benefits the actor(s) in some manner. Depending on the number of unique transactions that the use case must address, like actors, a use case can be categorized as being simple, average, or complex. A use case is classified as a simple use case if it supports one to three transactions, as an average use case if it supports four to seven transactions, or as a complex use case if it supports more than seven transactions. Once all of the use cases have been successfully categorized, the project manager will enter the number of each type of use case into the unadjusted use case weighting table contained in the use-case point–estimation worksheet. By multiplying by the appropriate weights and summing the results, we get the value for the unadjusted use case weight total (UUCW). Next, the project manager computes the value of the unadjusted use-case points (UUCP) by simply summing the unadjusted actor weight total and the unadjusted use-case weight total.

Use-case point–based estimation also has a set of factors that are used to adjust the use-case point value.

- Name two ways to identify the tasks that need to be accomplished over the course of a project.

The overall objectives for the system should be listed on the system request, and it is the project manager’s job to identify all of the tasks that need to be accomplished to meet those objectives.

- One approach for identifying tasks is to get a list of tasks that has already been developed and to modify it. There are standard lists of tasks or methodologies that are available for use as a starting point. (For example: methodology)

- The second approach would be the top to down approach whereby the high-level tasks are defined and then these are broken down into subtasks.

- What are the problems associated with conventional WBSs?

Most approaches to developing conventional WBSs tend to have three underlying problems:

- They tend to be focused on the design of the information system being developed. As such, the creation of the WBS forces the decomposition of the system design and the tasks associated with creating the design of the system prematurely. Where the problem domain is well understood, tying the structure of the work plan to the product to be created makes sense. However, in cases where the problem domain is not well understood, the analyst must commit to the architecture of the system being developed before the requirements of the system are fully understood.

- They tend to force too many levels of detail very early on in the SDLC for large projects or they tend to allow too few levels of detail for small projects. Since the primary purposes of a WBS is to allow cost estimation and scheduling to take place, in conventional approaches to planning, the WBS must be done “correctly and completely” at the beginning of the SDLC. To say the least, this is a very difficult task to accomplish with any degree of validity. These kinds of cases often lead to inaccurate cost and schedule estimation.

- Since they are project specific, they are very difficult to compare across projects. This leads to ineffective learning across the organization. Without some standard approach to create WBSs, it is difficult for project managers to learn from previous projects managed by others. This tends to encourage the “reinventing of wheels” and allows managers to make the same mistakes that previous managers have made.

- What is an evolutionary WBS? How do they address the problems associated with conventional WBSs?

Evolutionary work breakdown structure allows the project manager to provide more realistic estimates for each iteration or build of a system. They also allow the work plan to be decoupled from the architecture of the system, thus allowing projects to be comparable. By supporting comparability among projects, evolutionary WBSs enable organizational learning to take place.

Evolutionary WBSs allow the analyst to address all three of these problems by allowing the development of an iterative work plan :

- First, they are organized in a standard manner across all projects: by workflows, phases, and then tasks. This decouples the structure of an evolutionary WBS from the structure of the design of the product. This prevents prematurely committing to a specific architecture of a new system.

- Second, evolutionary WBSs are created in an incremental and iterative manner. The first evolutionary WBS is typically only done for the aspects of the project understood by the analyst. Later on, as the analyst understands more about the evolving development process, more details are added to the WBS. This encourages a more realistic view of both cost and schedule estimation.

- Third, since the structure of an evolutionary WBS is not tied to any specific project, evolutionary WBSs enable the comparison of the current project to earlier projects. This supports learning from past successes and failures.

- What is an iterative workplan?

Iterative work plans better fit the typical methodologies associated with object-oriented systems development. They allow the project manager to provide more realistic estimates for each iteration or build of a system. Furthermore, they allow the work plan to be decoupled from the architecture of the system, thus allowing projects to be comparable.

- What is scope creep, and how can it be managed?

Scope creep is the most common reason for schedule and cost overruns. The main factor contributing to this is when new requirements are added to the project after the original project scope was defined and frozen. There are other reasons such as: A user may suddenly understand the potential of the new system and realize new functionality that would be useful; a senior manager may decide to let this system support a new strategy that was developed at a recent board meeting etc.,

The keys are to identify the requirements as well as possible in the beginning of the project and to apply analysis techniques effectively. No matter what kinds of precautions are taken, a few factors may go unnoticed or unattended to but several practices can be helpful to control additions to the existing task list.

- The first thing that a project manager needs to do is to allow only absolute necessary requirements to be added after the project begins.

- Any change that is implemented should be carefully tracked so that an audit trail exists to measure the change’s impact.

- In some cases, beneficial changes cannot be incorporated into the present system, in which case these additions could be additions to scope as future enhancements to the systems.

- What is timeboxing, and why is it used?

Timeboxing is a technique that is used to organize a project when time is a critical issue. With timeboxing, a fixed deadline is established, and the project team prioritizes the functionality of the system so that the essential features are delivered within the set deadline. If some features must be omitted given that time frame, they are postponed to a later version of the system. With this technique, the users are assured of getting a system with essential functionality by the project deadline, and other, less essential features and refinements are added in later system versions

- Describe the hurricane model.

The estimates that are produced during the planning phase will need to be refined as the project progresses. The term 'hurricane model' describes the process by which estimates of project scope, schedule, and cost are repeatedly refined as more information is learned about the system. As the project progresses, more knowledge is gained that enables the estimates to be made more accurate and precise

- Create a list of potential risks that could affect the outcome of a project.

Weak personnel, scope creep, poor design decisions, overly optimistic project estimates

- Describe the differences between a technical lead and a functional lead. How are they similar?

Technical Lead: The technical lead is typically a project team member who supervises the programmers and more technically oriented project staff.

Functional Lead:  The functional lead is a team member who oversees the systems and business analysts on the team. Both positions report to the project manager, and are responsible for managing, controlling, and coordinating the work of their assigned team members

- Describe three technical skills and three interpersonal skills that would be very important to have on any project.

Desirable technical skills might include programming experience in the chosen programming language, experience in configuring the hardware and communications technology platform correctly, and experience in utilizing the file/database environment effectively. Desirable interpersonal skills might include interviewing skills, negotiation skills, and conflict resolution skills.

- What are the best ways to motivate a team? What are the worst ways?

Research has shown that technically oriented people are motivated by recognition, achievement, the work itself, responsibility, advancement, and the chance to learn new skills. The worst ways to motivate technical staff include setting unrealistic deadlines, failing to recognize good effort, accepting low quality output, rewarding all team members monetarily regardless of work quality, failing to include team members in important project decisions, and providing poor working conditions.

- List three techniques to reduce conflict.

Clearly define the roles on the project, hold team members accountable for their assigned tasks, develop detailed operating procedures and make sure the team members understand them, have each team member commit to the project charter.

- What is the difference between upper CASE (computer- aided software engineering) and lower CASE?

Upper CASE refers to diagramming and other tools that are commonly used during the Analysis phase of the SDLC. Lower CASE refers to diagramming and prototyping tools and code generators that are used primarily to support the Design phase of the SDLC. These two components of CASE products are targeted at different segments of the life

- Describe three types of standards, and provide examples of each.

Coding standards define the content and structures that are to be used in programs. An example would be that all programs are to be written following structured programming guidelines.

Procedural standards define processes that are to be followed by all team members. An example would be required attendance at a weekly team progress meeting, and required honest progress reporting at that meeting.

User interface design standards create a common understanding of the appearance and functioning of the screens the end users see. An example would be to create a standard group of icons that are used consistently on all screens.

- What belongs in the project binder? How is the project organized?

All project deliverables, all internal communication, and all project documentation should be placed in the project binder. The sections of the project binder should follow the phases of the life cycle, and each deliverable produced during the project should be placed in its appropriate place.