CHAPTER 2

PROJECT INITIATION

A. Locate a news article in an IT trade magazine (e.g., Computerworld) about an organization that is implementing a new computer system. Describe the tangible and intangible value that the organization likely will realize from the new system.

JULY 19, 2004 (COMPUTERWORLD) - In the late 1990s, Raytheon Co.'s Network Centric Systems (NCS) business unit in North Texas migrated to a new mainframe system that didn't include a materials tracking program. The result was pure bedlam. "A lot of stuff got lost, and we had no way to find it other than to go and look for it, and that could be a 15-minute or a 15-day process," says Vince Hrenak, vice president of supply chain at Raytheon. "We used to have multiple people sitting by the phones to take the calls asking where parts were."

NCS formed a cross-functional team to search for a remedy. It evaluated at least a half-dozen software packages as well as proposals solicited from commercial systems integrators before ultimately deciding to develop its own system. McKinney, Texas-based NCS had "a lot of specific business rules wrapped around custom processes," explains Rob Vettor, senior business technologist and chief architect of the new MTrak system. "What we wanted to gain was the advantage of avoiding software costs plus having a customized solution to our unique business problems," says Gene Feighny, MTrak's lead software engineer.

Now, a little more than two and a half years later, what began as a pilot project at NCS has blossomed into an enterprisewide supply chain application that supports 13 Raytheon sites and serves more than 20,000 users. And with cost savings directly attributed to MTrak totaling $8.6 million, other Raytheon sites are lining up to get MTrak. MTrak will eventually be deployed to 45,000 employees and is expected to cut costs by another $17 million. The $18 billion defense contractor projects total savings of $26 million over four years. "This is a rare victory, in my experience," says Hrenak.

http://www.computerworld.com/softwaretopics/erp/story/0,10801,94558,00.html

The tangible value from this system is is easily measured as $ 8.6 million dollars and is directly calculated from cost savings figures.  The projected total tangible value over the next four years is $ 26 million.  The intangible value would is not easily measured, but includes increased efficiency in material logistics, improved communication, better utilization of human resources, and potential sales of the Mtrak technology to other entities.

B. Car dealers have realized how profitable it can be to sell automobiles using the Web. Pretend you work for a local car dealership that is part of a large chain such as CarMax. Create a system request you might use to develop a Web-based sales system. Remember to list special issues that are relevant to the project.

System Request—Web-based sales system

Project Sponsor:	Matthew Moore, Sales Manager

Business Need:	This project has been initiated to reach new Internet customers and to better serve existing customers using Internet sales support.

Business Requirements:

Using the Web, customers should be able to search for vehicles, and identify the brick-and-mortar stores that have them in stock. They should be able to request vehicles not carried or not in stock, and receive notification if their requested vehicle becomes available.  The functionality of the system is listed below:

- Search through CarGo’s inventory of vehicles

- Identify the retail dealers that have them in stock

- Schedule an appointment to view the vehicle

- Place a request for a vehicle not currently in stock

- Receive notification that a requested vehicle is in stock

Business Value:

We expect CarGo’s sales will increase as a result of a wider scope of potential customers who can view our inventory, and request out of stock vehicles through CarGo’s Internet presence.  We expect the improved services to increase the number of customers who view vehicles at CarGo, and attract additional customers through the request/notification process because 60% of customers seek a specific vehicle model.  CarGo should benefit from increased customer satisfaction and brand recognition due to its Internet presence.

Conservative estimates of tangible value to the company includes:

- $750,000 in sales generated through web-based sales system

- $1,875,000 in sales from walk-in customers who are later notified via Web-based system

- $50,000 yearly reduction of telephone expenses associated with customer queries

# Special Issues or Constraints

- The Marketing Department views this as a strategic system.  The Internet system will add value to our current business model, and it also will serve as proof of concept for future Internet endeavors.  For example, in the future, if CarGo may want to sell vehicle service, or offer lease programs directly over the Internet.

- The system should be in place for the summer season next year.

Using the model System Request form provided in the textbook, have students prepare a System Request for the car dealer to improve its web-based sales.  Have students work in small groups, and then present their ideas to the class. Pay particular attention to the Functionality and Expected Value sections. How well have the students conveyed their ideas? Have both tangible and intangible benefits and costs been included? Do their requests seem persuasive?  You might have them post their requests around the room with blank pages for members of other groups to list questions or critiques of these requests.

C. Suppose that you are interested in buying yourself a new computer. Create a cost–benefit analysis that illustrates the return on investment that you would receive from making this purchase. Computer-related Web sites (e.g., Dell Computers, Compaq Computers) should have real tangible costs that you can include in your analysis. Project your numbers out to include a three-year period of time and provide the net present value of the final total.

| Cost Benefit Analysis |  |  | 2004 | 2005 | 2006G | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SchoolworkA |  |  | 3,000 | 3,100 | 3,200 |  |  |  |
| CommunicationB |  |  | 400 | 425 | 450 |  |  |  |
| EntertainmentC |  |  | 600 | 600 | 600 |  |  |  |
| Travel MoblityD |  |  | 400 | 400 | 400 |  |  |  |
| Digital Photo StorageE |  |  | 100 | 100 | 100 |  |  |  |
| Bill Payment F |  |  | 50 | 50 | 50 |  |  |  |
| Total Benefits |  |  | 4,550 | 4,675 | 4,800 |  |  |  |
| PV of BenefitsH |  |  | 4,550 | 4,289 | 4,040 | 12,879 |  |  |
| PV of All Benefits |  |  | 4,550 | 8,839 | 12,879 |  |  |  |
| Computer & Case (notebook) |  |  | 3,000 | 0 | 0 |  |  |  |
| Total Development Costs |  |  | 3,000 | 0 | 0 |  |  |  |
| Printing Costs |  |  | 75 | 80 | 85 |  |  |  |
| Electricity |  |  | 20 | 20 | 20 |  |  |  |
| Maintenance |  |  | 120 | 120 | 120 |  |  |  |
| Storage Media (CD's) |  |  | 35 | 35 | 35 |  |  |  |
| Total Operational Costs |  |  | 250 | 255 | 260 |  |  |  |
| Total Costs |  |  | 3,250 | 255 | 260 |  |  |  |
| PV of Costs |  |  | 3,250 | 234 | 219 | 3,703 |  |  |
| PV of All Costs |  |  | 3,250 | 3,484 | 3,703 |  |  |  |
| Total Project Benefits--Costs: |  |  | 1,300 | 4,420 | 4,540 |  |  |  |
| Yearly NPV: |  |  | 1,300 | 4,055 | 3,821 | 9,176 |  |  |
| Cumulative NPV: |  |  | 1,300 | 5,355 | 9,176 |  |  |  |
| Return on Investment: |  |  | 247.82% |  |  |  |  |  |
| Break-even Point: |  |  | 1 year |  |  |  |  |  |
| Intangible Benefits: |  |  | Ease of use of new design compared to old computer |  |  |  |  |  |
|  |  |  | Increases your value to an internship co.since you have computer |  |  |  |  |  |
|  |  |  | Future potential for virtual-office applications to improve group work |  |  |  |  |  |
| Assumptions: |  |  |  |  |  |  |  |  |
| A - If annual tuition is $30,000, then assume 10% annual computer benefit or $30,000*.10 = $3000 |  |  |  |  |  |  |  |  |
| B - Includes email, messaging (voice & video), conferencing, and long distance expense savings |  |  |  |  |  |  |  |  |
| C - Includes net surfing, music, video, gaming, etc. |  |  |  |  |  |  |  |  |
| D - Includes 3 flights annually with 4 hours of computer work during travel, personal time = $25/hr |  |  |  |  |  |  |  |  |
| E - Includes savings from printing photos and maintaining hard photo albums |  |  |  |  |  |  |  |  |
| F - Includes postage and check savings |  |  |  |  |  |  |  |  |
| G - Assume will be student throughout 2006 |  |  |  |  |  |  |  |  |
| H - Assume student loan rate is 9%, so interest rate = 9% |  |  |  |  |  |  |  |  |

D.  Consider the Amazon.com Web site. The management of the company decided to extend their Web-based system to include products other than books (e.g., wine, specialty gifts). How would you have assessed the feasibility of this venture when the idea first came up? How “risky” would you have considered the project that implemented this idea? Why?

It’s important to consider the three components of feasibility: technical, economical, and organizational.

The technical feasibility to expand the range of products sold on Amazon looks very promising.  Since the current IT system can easily be modified to include the additional items, the risk of adding the additional sales application to the business process is minimum.  In addition, its important to consider the scope of the new items offering as a large offering will require more complex system work than a small offering that can more easily be implemented into the current process.  Larger projects carry more risk.

The Economic feasibility can easily be addressed through a cost-benefit analysis.  Amazon will require some development costs to broaden their product range, however since the basic system is in place the costs of additional development will be minimum.  Operation costs will increase slightly, however since many of the functions that drive operational costs are currently covered by the existing system, additional operational costs will be minimum also.  Most significant are the benefits or additional revenue generated by wider product offerings.  Its important Amazon carefully selects products that will generate the most sales, and provide the highest profit. This careful selection will help minimize economic risk.

The organizational feasibility is very good.  Additional product offering will gel with the current market strategy, and add increased benefits.  Many stakeholders will benefit from the new system such as customers, shareholders, vendors, and employees.  The project will be less risky if an effective champion leads the company though the implementation of the new project.

Overall, I would consider this to be a low risk project.

E.  Interview someone who works in a large organization and ask him or her to describe the approval process that exists for approving new development projects. What do they think about the process? What are the problems? What are the benefits?

I spoke to a former operations employee of a medium sized airline.  We discussed the airlines implementation of a new frequent fliers IT system that replaced the former paper system.  The new system utilized magnetic strip membership cards that were used by customers to check-in as well as a database to store customer information.

The operations department first conceived the idea to improve the frequent flier program, and then researched various methods.  Once they decided to pursue the plastic card database option they obtained samples from vendors, and sent the request to company headquarters.  There, a team compared the features of the new system to the ones of competitors, and identified advantages and disadvantages.  In addition they performed a detailed cost analysis, and feasibility study.

The new system was approved and provided effective data management and fit well with the company’s long-term goals.  The most significant problem of the approval process was the length of time it took from conception to approval to implementation.  The benefits of the process were the resulting well-planned system that provided effective passenger data and traceability, and the increased customer satisfaction.

F.  Reread the “Your Turn 2-1” box (Identify Tangible and Intangible Value). Create a list of the stakeholders that should be considered in a stakeholder analysis of this project.

### Internal

- Operation Employees - service engineers are system users

- IT Employees – implement the system & manage change

- Managers – benefit from efficiency, profitability, and bonuses

- Shareholders – financial gain from efficiency & profitability

### External

- Customers – (wholesale and retail) – benefit from better response to problems

- IT Suppliers – new system will require purchase of technology, equipment, and services

- Map Suppliers – loose map supply business to new system, however may provide consultation to supply data for new system

H. Visit a project management Web site, such as the Project Management Institute (www.pmi.org). Most have links to project management software products, white papers, and research. Examine some of the links for project management to better understand a variety of Internet sites that contain information related to this chapter.

Purpose: to gain a broader appreciation for IT project management and resources available for further study in the area.

www.pmi.org

A brief inspection of the page shows that there is more information that would be of general interest to project managers than there is information on how to use IT in project management.  It might be of interest to have your students do something of a scavenger hunt for “project management software products” information using this page with detailed instructions for finding the information again.  Sharing nuggets found with the rest of the class members would be helpful.

I. Select a specific project management topic such as CASE, project management software, or timeboxing and search for information on that topic using the Web. The URL listed in exercise A or any search engine (e.g., Bing, Google) can provide a starting point for your efforts.

Purpose: to extend the student’s awareness of resources available to pursue specialized topics; resources for a special topic of interest.

Two variations on this exercise would be to allow students to decide on their own topics.  It would be of interest to see the variety of topics selected.  Or the instructor can provide topics for students.  The instructor can either provide all students with the same topic, such as CASE tools to see what sort of variance in items found will be (and demonstrate the vast array of materials); or can provide a variety of topics, perhaps having students pull them from a hat.  In either case, students are likely to find a vast array of materials on the web that are not particularly helpful and sometimes that look helpful but really boil down to advertising or hype.  It will be important to review what the students find and provide some feedback regarding how to evaluate these materials.

J. Pretend that the career services office at your university wants to develop a system that collects student résumés and makes them available to students and recruiters over the Web. Students should be able to input their résumé information into a standard résumé template. The information then is presented in a résumé format, and it also is placed in a database that can be queried using an online search form. You have been placed in charge of the project. Develop a plan for estimating the project. How long do you think it would take for you and three other students to complete the project? Provide support for the schedule that you propose.

Purpose: to practice converting a project idea into specific tasks, and to add consideration of specific people to task planning.

It is not a bad idea to do the exercise in class where you can “enforce” sequential progress from listing tasks to adding a deadline to adding time lengths and personnel to each task.  If you assign all three, you might ask students to keep a log of how they go about the task – performing this ad hoc, the students may consider times for each task as they think of it rather than list all tasks then assign times.  Does it matter which way they do this?  Chances are, they will need to go through more than one iteration anyway.  Assigning this set of exercises to 4 person teams could be interesting as they should list all tasks then allocate out the activities among themselves performing some sort of negotiation.  Depending on the background of the students, they may or may not need to plan in some training to be prepared to handle all the tasks.

K. Refer to the situation in exercise J. You have been told that recruiting season begins a month from today and that the new system must be used. How would you approach this situation? Describe what you can do as the project manager to make sure that your team does not burn out from unreasonable deadlines and commitments.

Purpose:  to practice converting a project idea into specific tasks and to add discussion of time and personnel tradeoffs.

The mini-case presents the students the students with a deadline in addition to the previously described functional requirements.  It is important to consider “starting backwards” in terms of when the project is to be completed and when each task must be started in order to complete on time.  This is a good place to discuss ways to break tasks up into smaller units, but additionally the cost of coordination and putting smaller units back together.

L. Consider the system described in exercise J. Create a workplan listing the tasks that will need to be completed to meet the project’s objectives. Create a Gantt chart and a network diagram in a project management tool (e.g., Microsoft Project) or using a spreadsheet package to graphically show the high level tasks of the project.

Purpose: to practice converting a project idea into specific tasks and to provide an experience of charts.

It can be helpful to introduce the idea of mini-milestones and deliverables at this point.  This can also be a good exercise for using MS Project or a similar tool if one is available for displaying the results.  Interestingly, the activities can be presented in hierarchical fashion conforming to the various aspects of the project as presented in the exercise description.  The question should arise from students as to how detailed the final task descriptions should be.  This is a good place to discuss variations among stakeholders – even within the project team – and the different users of and uses for the task plan.

You may show a Gantt and Pert charts as part of the PowerPoint slides used in lecturing.  Students get the idea for this very quickly.  MS Project is effective for listing the mini-milestones or work tasks, MS Project very easily transforms these automatically into chart format for printing out.  If your students do not have MS Project available in the lab, you might still find one for display in class.

M. Suppose that you are in charge of the project that is described in exercise J and the project will be staffed by members of your class, do your classmates have all the right skills to implement such a project? If not, how will you go about making sure that the proper skills are available to get the job done?

Purpose:  to focus on skills required for project completion.

How are students to go about this?  It would seem logical to list out skills needed to perform each of the tasks identified in exercises J through L and also to list out the skills that each student possesses.  Note that activities needed to enhance skill sets must also be added into the overall listing of tasks with their time and costs accounted for.

It would be interesting to assign exercise M to each member of each group that participated in J through L to perform individually.  Students in comparing their findings will see if the student’s assessment of her or his skills matches the assessment made by fellow team members.  How will they reconcile these differences?  How exact can the specification of skills needed for each task be made?

N. Complete a use-case point worksheet to estimate the effort to build the system described in exercises J, K, L, and M. You will need to make assumptions regarding the actors, use cases, and the technical complexity and environmental factors.

Purpose:  To provide an experience of use-case point estimation.

The danger, of course, is the students cannot categories the complexity of actors or use cases, and they may have difficult to adjust the efforts based on the factors discussed in page 26.  Students can follow the steps discussed in page 24 to page 26 and the example in page 26 to try different assumptions of the complexity categorization and the adjustment.

O. Consider the application that is used at your school to register for classes. Complete a use-case point worksheet to estimate the effort to build such an application. You will need to make some assumptions about the application’s interfaces and the various factors that affect its complexity.

Purpose:  To provide an experience of function point calculation.

You can do this with hypothetical numbers in class.  Students can pick numbers “randomly” or for a case that they are working on just to demonstrate how to do the calculation.  The danger, of course, is the students missing that the numbers are in fact based on “reality” and their specifics are critical to further decision-making.  If you do this with the registration system at your school, it might be helpful to bring in someone from the IT department.  Your students will be surprised at how much of the system resides under the covers and is not readily visible to them as users.

P. Read Your Turn 2-6. Create a risk assessment that lists the potential risks associated with performing the project, along with ways to address the risks.

Purpose:  To focus on the various types of risks that follow from a real project.

Students often will identify risks that are quite similar (all in the financial area for example).  It is valuable to ask them to select a technical, financial, and organizational risk.  It is not so important, in the long-run, how these are categorized but it is critical that the full range of risks are identified.  To push this further, for each risk identified, ask how the students would track progress relative to the risk and what actions would tend to minimize the risk.

Q. Pretend that your instructor has asked you and two friends to create a Web page to describe the course to potential students and provide current class information (e.g., syllabus, assignments, readings) to current students. You have been assigned the role of leader, so you will need to coordinate your activities and those of your classmates until the project is completed. Describe how you would apply the project management techniques that you have learned in this chapter in this situation. Include descriptions of how you would create a workplan, staff the project, and coordinate all activities— yours and those of your classmates.

Purpose:  To integrate the various project management approaches already presented.

It may be of value to insure that the students follow through on each of the project management activities.  If they don’t do these sequentially, they should still do all of them.  Note that the identification of risks may lead to additional activities that need to be listed, timed, and assigned to individuals.

R. Select two project management software packages and research them using the Web or trade magazines. Describe the features of the two packages. If you were a project manager, which one would you use to help support your job? Why?

Purpose:  To consider software that supports project management.

A Google search on “project management software” yielded over 2 million pages returned.  A very good place to look however (as of June 2002) is the following website:

http://www.project-management-software.org/project/

A large number of software tools are listed and partly evaluated on this site.  Students may find some they can download and check out for free.

Instructors may ask students to define criteria for assessing these software tools.  It is interesting to see the differences in what students list if they do this before or after examination of a particular tool.

T. In 1997, Oxford Health Plans had a computer problem that caused the company to overestimate revenue and underestimate medical costs. Problems were caused by the migration of its claims processing system from the Pick operating system to a UNIX-based system that uses Oracle database software and hardware from Pyramid Technology. As a result, Oxford’s stock price plummeted, and fixing the system became the number-one priority for the company. Suppose that you have been placed in charge of managing the repair of the claims processing system. Obviously, the project team will not be in good spirits. How will you motivate team members to meet the project’s objectives?

Purpose: to focus on motivation and personnel issues.

The instructor might want to encourage students to use what they know about what motivates them to work harder as well as what they learned in management courses to supplement the discussion in the book.  A side benefit of this exercise is that the instructor may infer something about the factors the class members see as motivating themselves – for use in motivating the students to perform at a high level.

Overall note regarding this chapter:  For many students, participating in projects is fairly routine, but applying what they have learned to participating specifically in IT projects is not necessarily intuitive.  Understanding the dimensions and quirks of IT project activities ultimately takes experience and practice – this chapter and these exercises should heighten awareness of what to look for, but will be unlikely to result in expert project managers.